## Slide 1: WSJF Workshop

## Slide 2: Agenda
Introduction to WSJF
When to Use
Calculating WSJF
Example Scenario
WSJF Template
Let’s WSJF
Q & A

## Slide 3: Introduction to WSJF
WSJF noun: (wiz – jiff); verb: (wiz – jiffed); Acronym for Weighted Shortest Job First
  A Prioritization method used to determine the highest value work by comparing the ratio of Delay Cost and Effort.
= WSJF Score
Effort
Delay Cost
WSJF Formula
For each item in the list, we need to calculate a WSJF Score, using a consistent formula.
To do so, we need to determine each item’s Delay Cost (aka “Cost of Delay”), and Effort.

## Slide 4: When to Use
Program Backlog: There are multiple teams operating under the SAFe Framework, getting ready to launch a new Agile Release Train. For PI Planning, leadership needs to confirm what the top priorities are for teams to work on in the upcoming quarter.
Post-Strategic Planning: A Strategic Themes Breakdown workshop was recently completed, and there is a laundry list of things to do in the upcoming year. This list needs to be quickly prioritized to ensure the highest value items are accomplished first.
Product Management New Features: Product Management has a long list of features they want to add to their product line. They need to quickly understand which features are most important to get to production first.
Unprioritized List: You have a list of items you need to complete, and not enough resources to do everything at once. You need to prioritize based on value and effort. Any Unprioritized list? Yes, you can even use WSJF at home for Do-It-Yourself (DIY) Home Improvement.

## Slide 5: Calculating WSJF
Variables and Scoring

## Slide 6: Delay Cost
Is the sum of three variables: Value, Urgency, Safer/Better.
Value
How much value will will it bring? Customer Satisfaction,
Increased Revenue, Decreased Expenditure
Urgency
How Urgent is the item? Now…, By end of…, At some point…
Safer/Better
How much Safer/Better will we be? Reduced Risk, Unlocked Opportunity, Faster Delivery
= WSJF Score
Effort
Delay Cost
WSJF Formula

## Slide 7: Effort
Is an estimate of how much work this item represents.
It represents all work associated with this item including:
planning, coordination, communications, development/build, deployment, quality assurance, and any post-deployment related work or follow-ups.
Effort Is not duration

## Slide 8: How to Score
We’ll use Fibonacci values from 1 to 21 for relative scoring
Relative scoring: each score is relative to each other, not relative to an external measurement.
Fibonacci was a mathematician who identified a number sequence where each number is based on the sum of the two prior numbers.
The sequence is associated with spirals and is found commonly in nature.
1, 2, 3, 5, 8, 13, 21
(1+2 = 3, 3+5 = 8, etc…)
Value:
Urgency:
Safer/Better:
Effort:
1: Low Value 21: The Most Value
1: Low Urgency 21: Starts Now
1: Low Impact 21: Very High Impact
1: Low Effort 21: Very, Very Large
Delay
Cost
{
Note: The value of using Fibonacci is that it compounds as it grows, which correlates with our human ability to understand complex things.

## Slide 9: Introduction to WSJF
WSJF noun: (wiz – jiff); verb: (wiz – jiffed); Acronym for Weighted Shortest Job First
  A Prioritization method used to determine the highest value work by comparing the ratio of Delay Cost and Effort.
= WSJF Score
(Value + Urgency + Safer/Better)
Effort
Delay Cost
WSJF Formula
For each item in the list, we need to calculate a WSJF Score, using a consistent formula.
To do so, we need to determine each item’s Delay Cost (aka “Cost of Delay”), and Effort.

## Slide 10: Example Scenario

## Slide 11: WSJF Example
In your own home there are several repairs or improvements that need to be made. You’ve made a list and now need to determine which items to work on first.
Build a Shed
Install 3 New Fire Alarms
Repaint the Bedrooms
Value:
Urgency:
Safer/Better:
Effort:

## Slide 12: WSJF Example
In your own home there are several repairs or improvements that need to be made. You’ve made a list and now need to determine which items to work on first.
Build a Shed
Install 3 New Fire Alarms
Repaint the Bedrooms
Value:
Urgency:
Safer/Better:
Effort:
13
2
1
13
5
3
2
5
1
8
8
2

## Slide 13: WSJF Example
In your own home there are several repairs or improvements that need to be made. You’ve made a list and now need to determine which items to work on first.
Build a Shed
Install 3 New Fire Alarms
Repaint the Bedrooms
Value:
Urgency:
Safer/Better:
Delay Cost:
Effort:
WSJF Score:
13
2
+ 1
16
13
5
3
+ 2
10
5
1
8
+ 8
17
2
16/13 = 1.23
10/5 = 2
10/5 = 8.5

## Slide 14: WSJF Example
In your own home there are several repairs or improvements that need to be made. You’ve made a list and now need to determine which items to work on first.
Build a Shed
Install 3 New Fire Alarms
Repaint the Bedrooms
Value:
Urgency:
Safer/Better:
Delay Cost:
Effort:
WSJF Score:
13
2
+ 1
16
13
5
3
+ 2
10
5
1
8
+ 8
17
2
16/13 = 1.23
10/5 = 2
10/5 = 8.5
Do FIRST!
Do SECOND!
Do LAST!

## Slide 15: WSJF Example
Given the WSJF Scores, the fire alarms should be installed first. Then the bedrooms painted, and after that the shed built.
Do you disagree? Why or Why Not?

## Slide 16: WSJF Template
DIY Home Improvement List | Value | Urgency | Safer/ Better | Delay Cost | Effort | WSJF Score
Landscaping |  |  |  |  |  | 
Fix Broken Hot Water Heater |  |  |  |  |  | 
Clean the Pool |  |  |  |  |  | 
Repaint the Bedrooms | 5 | 3 | 2 | 10 | 5 | 2
Add 3 Fire Alarms | 1 | 8 | 8 | 17 | 2 | 8.5
Replace Up-stairs Toilet |  |  |  |  |  | 
Build a Shed | 13 | 2 | 1 | 16 | 13 | 1.23
Backlog
= WSJF Score
(Value + Urgency + Safer/Better)
Effort
Delay Cost
WSJF Formula

## Slide 17: Questions? Let’s WSJF!