## Instructions
Feature Breakdown — Story Map Template
Stephens Insight Group ¦ stephensinsightgroup.com
How to use this template
1. | Fill in the Feature Overview tab first — the feature name, business objective, and scope boundaries agreed with the Product Owner.
2. | During Story Mapping, use the Story Map tab to lay out user activities (backbone) across the top and the user stories under each activity, in priority order top to bottom.
3. | Move finalized stories to the Story Backlog tab. Add acceptance criteria, dependencies, size, and priority for each — this becomes the sprint-ready backlog.
4. | Log any cross-team or cross-system dependencies on the Dependencies tab as they surface during the session — don't wait until the end.
5. | Export or copy the Story Backlog tab into your team's backlog tool (Jira, Azure DevOps, Rally) as part of workshop follow-up.
Cells shaded gold are where the facilitator or team should type.
This template accompanies the Feature Breakdown Workshop Guide at stephensinsightgroup.com/feature-breakdown-workshop/

## Feature Overview
Feature Overview
Confirm this with the Product Manager / PO before the session
Feature Name
Business Objective / Value Statement
In Scope
Out of Scope (explicitly)
Product Manager / PO
Facilitator
Session Date
Participants

## Story Map
Story Map — Backbone and Stories
Backbone (user activities) across the top; stories underneath, top = highest priority
Activity 1 | Activity 2 | Activity 3 | Activity 4 | Activity 5 | Activity 6

## Story Backlog
Story Backlog — Sprint-Ready
Move finalized stories here with acceptance criteria, sizing, and priority
Story ID | User Story (As a... I want... So that...) | Acceptance Criteria | Dependencies | Story Points / T-Shirt Size | Priority (WSJF or MoSCoW) | Owner | Status
FB-01 | As a claims processor, I want to filter claims by status so that I can prioritize my daily queue. | Given a list of claims, when I select a status filter, then only claims matching that status display. | Depends on claims-status API (Platform team) | 3 | High | Jane D. | Ready

## Dependencies
Cross-Team / Cross-System Dependencies
Log dependencies as they surface — don't wait until the end of the session
Dependency | Related Story ID(s) | Owning Team / System | Resolution Needed By | Status