## Slide 1
WORKSHOP GUIDE
Portfolio Kanban Workshop

## Slide 2
Agenda
- Introduction to Portfolio Kanban
- When to Use
- The Kanban Board & Flow
- WIP Limits
- Example Scenario
- Portfolio Kanban Template
- Let's Kanban
- Q & A

## Slide 3
Introduction to Portfolio Kanban
Portfolio Kanban noun: (kan-bahn); a visual system for managing the flow of epics from idea to value.
- A method used to make the flow of work visible, and to expose where it is stuck, by limiting how much can be in progress at once.
For every epic on the board, we track a consistent set of things: its stage, how long it has been there, and whether its stage is within its WIP limit.
Core Principle
Visualize the Work
then
Limit Work in Process
then
Manage & Improve Flow

## Slide 4
When to Use
Too Many Epics in Flight: Teams are context-switching across more initiatives than they can actually execute well.
Work Stalls in Analysis: Good ideas sit in review or approval for months with no visibility into why.
No Clear View of Status: Leadership can't answer what the team is working on right now without pulling several reports.
Resetting Lean Portfolio Management: The organization is establishing or resetting its LPM practice and needs a shared operating model.

## Slide 5
The Kanban Board
Stages and Flow

## Slide 6
Board Stages
The board is organized into five stages. Work-in-process (WIP) limits are applied to each stage to prevent overload and expose bottlenecks early.
Funnel
Ideas enter here
>
Reviewing
Analysis & business case
>
Portfolio Backlog
Approved, awaiting capacity
>
Implementing
Active development
>
Done
Value delivered
Each stage has its own WIP limit -- a maximum number of epics allowed at once.

## Slide 7
WIP Limits
A cap on the number of epics allowed in a stage at the same time.
A WIP limit IS
A forcing function: when a stage is full, the team must finish something before starting something new -- exposing exactly where flow is breaking down.
A WIP limit IS NOT
A punishment, or a hard rule that can never flex. It is a signal to swarm and finish work, not a wall to work around.
Note: The value of a WIP limit compounds over time -- as flow improves, the team can safely lower limits further and go even faster.

## Slide 8
How to Read the Board
Look for two signals: items sitting far longer than normal (aging), and stages holding more than their WIP limit (overloaded).
- Aging: an epic that has been in one stage far longer than similar items.
- Overloaded: a stage holding more epics than its WIP limit allows.
- Blocked: an item that cannot move forward without an external decision.
Little's Law
Average Time in System
=
Work in Process / Throughput
Lower WIP moves faster.

## Slide 9
What to Track
A handful of simple metrics tell the whole flow story:
Cycle Time: How long an epic takes from Funnel to Done.
Throughput: How many epics reach Done per period.
Aging WIP: How long each in-progress epic has sat in its current stage.
Blocked Items: Epics that cannot move without an external decision.

## Slide 10
Example Scenario

## Slide 11
Portfolio Kanban Example
Your portfolio has three active epics. You need to place them on the board and check their flow.
Migrate Core Platform
Launch Partner Portal
Automate Compliance Reporting
Stage:
Days in Stage:
Within WIP Limit?

## Slide 12
Placing the Epics
Epic
Stage
Days in Stage
Within WIP Limit?
Migrate Core Platform
Implementing
12 days
Yes
Launch Partner Portal
Reviewing
41 days
No - over limit
Automate Compliance Reporting
Portfolio Backlog
6 days
Yes

## Slide 13
Spot the Bottleneck
Launch Partner Portal has been in Reviewing for 41 days -- well past the stage's normal cycle time, and the stage is already over its WIP limit.
Launch Partner Portal
Reviewing - 41 days - Over WIP limit
This is a bottleneck: work is piling up here faster than it's moving out.

## Slide 14
Discuss: What's Blocking It?
As a group, discuss why Launch Partner Portal has stalled in Reviewing:
- Is the business case waiting on an approval?
- Is a dependency blocking analysis?
- Is there a capacity conflict with another value stream?
- Is ownership unclear?

## Slide 15
Portfolio Kanban Example
Given the board, Launch Partner Portal is the clear bottleneck -- it should be swarmed and resolved before starting any new work in Reviewing.
Do you disagree? Why or why not?

## Slide 16
Portfolio Kanban Template
WIP Limit Rule
Items in Stage <= WIP Limit
If not, stop starting -- start finishing.
Epic
Owner
Stage
Days in Stage
WIP Limit
Status
Migrate Core Platform
Value Stream A
Implementing
12
5
OK
Launch Partner Portal
Value Stream B
Reviewing
41
3
Over
Automate Compliance Reporting
Value Stream A
Portfolio Backlog
6
6
OK

## Slide 17
Questions?
Let's Kanban!