## Portfolio Kanban Board
Epic | Owner / Value Stream | Stage | Date Entered Stage | Days in Stage | WIP Limit | Items in Stage | Status
Migrate Core Platform | Value Stream A | Implementing | 2026-07-18 | 12 | 5 | 1 | OK
Launch Partner Portal | Value Stream B | Reviewing | 2026-06-19 | 41 | 4 | 1 | OK
Automate Compliance Reporting | Value Stream A | Portfolio Backlog | 2026-07-24 | 6 | 6 | 1 | OK
Legend
Gold cells: enter your epic, owner, stage, and the date it entered that stage.
Gray cells: calculate automatically -- days in stage, that stage's WIP limit, how many items are currently in it, and whether it's over.
Set each stage's WIP limit on the 'WIP Limits' tab.
Formulas:
Days in Stage = IF([Date Entered Stage]="","",TODAY()-[Date Entered Stage])

## WIP Limits
Stage | WIP Limit | Items Currently in Stage | Status
Funnel | 3 | 0 | OK
Reviewing | 4 | 1 | OK
Portfolio Backlog | 6 | 1 | OK
Implementing | 5 | 1 | OK
Done | 99 | 0 | OK
Note: 'Done' is left effectively unlimited (99) since completed epics are not work in process.

## Produced By
Portfolio Kanban Template
Produced by Stephens Insight Group
stephensinsightgroup.com ¦ info@stephensinsightgroup.com ¦ (616) 724-0297
© 2026 Stephens Insight Group LLC. All rights reserved.