## Slide 1
Road Mapping
Workshop
Workshop Facilitator's Guide
A step-by-step guide for facilitating a Road Mapping session that aligns teams around strategic priorities and builds a shared execution plan.
Stephens Insight Group
Road Mapping Workshop Facilitator's Guide | 1

## Slide 2
OVERVIEW
What Is Road Mapping?
Stephens Insight Group
Road Mapping Workshop Facilitator's Guide | 2
Road Mapping is a collaborative workshop that helps leadership teams translate strategic priorities into a clear, time-bound execution plan.
Unlike a traditional roadmap tool, this session is about alignment — bringing the right people together to agree on what matters most and how to sequence the work.
The outcome is a shared, visible roadmap that every team member can connect their daily work to.
DURATION
2 – 4 hours (full session)
Can be split across two sessions
PARTICIPANTS
6 – 15 people
Leadership, product owners, key stakeholders
OUTCOME
A prioritized roadmap aligned to strategy with clear ownership and timelines

## Slide 3
SESSION SETUP
The Road Mapping Canvas
Stephens Insight Group
Road Mapping Workshop Facilitator's Guide | 3
Before the session begins, prepare the canvas. This becomes the shared workspace for the entire workshop.
ROAD MAPPING CANVAS
STRATEGIC THEMES
Top organizational priorities driving this roadmap
INITIATIVES & EPICS
Major bodies of work mapped to each theme
TIMELINE & MILESTONES
Quarters, sprints, or PI intervals with key dates

## Slide 4
SESSION FLOW
How Road Mapping Works
Stephens Insight Group
Road Mapping Workshop Facilitator's Guide | 4
The session moves through six structured steps. Each step builds on the last — do not skip ahead.
1
Set Context
Share strategy & goals
(15 min)
2
Identify Themes
Capture strategic priorities
(20 min)
3
Generate Initiatives
Brainstorm work bodies
(25 min)
4
Map & Sequence
Place on timeline
(25 min)
5
Assign Ownership
Name owners per initiative
(15 min)
6
Commit & Close
Confirm, capture, publish
(20 min)

## Slide 5
SESSION FLOW — STEPS 1 & 2
Setting Context and Identifying Themes
Stephens Insight Group
Road Mapping Workshop Facilitator's Guide | 5
STEP 1 — Set Context (15 min)
Open with a brief recap of the organization's strategy, goals, and OKRs for the planning period.
Share any constraints: budget, capacity, regulatory, or technology limitations the team must work within.
Clarify the planning horizon — are we mapping for one quarter, two quarters, or a full year?
Set ground rules: every voice matters; decisions stay in the room until published.
STEP 2 — Identify Themes (20 min)
Ask each participant to write strategic themes on sticky notes — one theme per note. Give 5 minutes of silent writing.
Each person shares their themes aloud; the facilitator posts them on the canvas under the Themes swim lane.
Group similar themes together. Name each cluster with a short, clear label that the whole team agrees on.
Vote to confirm the top 3–5 themes that will drive the roadmap. Dot voting or thumb voting both work well.

## Slide 6
SESSION FLOW — STEPS 3 & 4
Generating Initiatives and Sequencing
Stephens Insight Group
Road Mapping Workshop Facilitator's Guide | 6
STEP 3 — Generate Initiatives (25 min)
For each confirmed theme, ask participants: "What major bodies of work must we do to advance this theme?"
Write initiatives on sticky notes — one initiative per note. These are epics or large features, not tasks.
Post initiatives under the corresponding theme on the canvas. Duplicates are fine — they signal priority.
As a group, consolidate duplicates and clarify any initiatives that are too vague or too small in scope.
STEP 4 — Map & Sequence (25 min)
Move initiatives into the Timeline swim lane. Place them in the quarter or PI interval they are expected to begin.
Identify dependencies: draw a line or note when one initiative must precede another.
Discuss sequencing conflicts openly — what must come first? What can run in parallel?
Look for overloading: if one quarter has too many initiatives, redistribute or defer lower-priority items.

## Slide 7
SESSION FLOW — STEPS 5 & 6
Assigning Ownership and Closing the Session
Stephens Insight Group
Road Mapping Workshop Facilitator's Guide | 7
STEP 5 — Assign Ownership (15 min)
For each initiative on the canvas, identify and name the lead owner — the person accountable for execution.
Owners do not have to be in the room, but someone present must agree to confirm or recruit them.
Record the owner name on the canvas sticky note. If ownership is unclear, flag it — do not leave it blank.
Confirm that each owner has the capacity and context needed. Surface resource conflicts now, not later.
STEP 6 — Commit & Close (20 min)
Walk through the completed canvas as a group. Ask: "Does this represent our shared commitment?"
Capture any open items, decisions deferred, or questions that need follow-up outside this session.
Photograph or digitize the canvas immediately — within 24 hours post-session is best practice.
Identify who will publish the roadmap, where it will live, and when the first check-in will occur.

## Slide 8
CLOSING THE SESSION
After the Workshop
Stephens Insight Group
Road Mapping Workshop Facilitator's Guide | 8
1
Digitize Within 24 Hours
Transfer the physical canvas to a digital tool (Miro, Jira, or a shared document) while context is fresh.
2
Distribute the Roadmap
Share a clean version of the roadmap with all participants and key stakeholders within 48 hours.
3
Confirm Ownership
Reach out to any owners not present in the session to confirm their initiatives and capacity.
4
Schedule the First Check-in
Set a recurring review — monthly or per PI — to assess roadmap health and adjust as needed.
5
Connect to Team Backlogs
Break each initiative into epics and features. Link roadmap items to team-level work in your planning tool.
6
Measure and Communicate
Define how progress will be tracked and reported. Visibility keeps the roadmap alive and actionable.

## Slide 9
FACILITATOR GUIDANCE
Anti-Patterns to Avoid
Stephens Insight Group
Road Mapping Workshop Facilitator's Guide | 9
Watch for these common traps. Naming them early helps the group self-correct during the session.
Skipping the Context Step
Teams jump to solutions before aligning on strategy. Without shared context, initiatives lack coherent direction.
Too Many Themes
More than five themes dilutes focus. Push the group to make hard choices — not everything can be a priority.
Initiatives That Are Too Small
Tasks and stories belong in the backlog, not on the roadmap. Keep items at the epic or major feature level.
No Named Owners
An initiative without a clear owner rarely gets done. Anonymous accountability is no accountability at all.
Roadmap Lives Only on a Whiteboard
The canvas must be digitized and distributed. A physical artifact that no one can access after the session is wasted effort.
No Review Cadence Set
A roadmap without a review schedule becomes stale within weeks. Book the next review before leaving the room.

## Slide 10
Ready to facilitate?
Connect with Stephens Insight Group for coaching, templates, and hands-on facilitation support.
stephensinsightgroup.com | info@stephensinsightgroup.com | (616) 724-0297
Stephens Insight Group
Road Mapping Workshop Facilitator's Guide | 10