## Slide 1
MoSCoW
Prioritization
Workshop Facilitator's Guide
A structured technique for aligning teams on what truly matters — so the right work gets done first and scope stays under control.
STEPHENS INSIGHT GROUP
stephensinsightgroup.com

## Slide 2
OVERVIEW
What Is MoSCoW Prioritization?
MoSCoW is a prioritization framework that categorizes requirements, features, or tasks into four buckets based on their importance to project success. Originally developed by Dai Clegg in 1994 for DSDM (Dynamic Systems Development Method), MoSCoW gives teams a shared language for tough priority conversations — replacing "everything is important" with clear, defensible distinctions.
M
Must Have
Non-negotiable. The project fails without these items.
S
Should Have
Important but not critical. Include if resources allow.
C
Could Have
Nice-to-haves with minimal impact if excluded.
W
Won't Have
Explicitly out of scope this iteration — revisit later.
STEPHENS INSIGHT GROUP
stephensinsightgroup.com

## Slide 3
SESSION SETUP
Materials & Room Preparation
Set up before participants arrive — physical or virtual. The right environment removes friction and lets the group focus on decisions.
In-Person Setup
Whiteboard or large paper divided into 4 labeled zones: Must Have | Should Have | Could Have | Won't Have
Sticky notes (one color per category aids visual scanning)
Markers for each participant — thick enough to read from a distance
3 dot stickers per participant for contested-item voting
Timer visible to the whole group (clock or phone)
Scribe assigned in advance to document final decisions
Virtual Setup
Digital board (Miro, MURAL, FigJam) with 4 labeled columns pre-built
Sticky note template ready so participants don't waste time formatting
Voting feature enabled — dot votes, emoji reactions, or a polling tool
Shared countdown timer visible to all participants
Screen share on throughout — facilitator drives the board
Breakout rooms optional for small-group pre-sorting before plenary
STEPHENS INSIGHT GROUP
stephensinsightgroup.com

## Slide 4
SESSION FLOW
How MoSCoW Prioritization Works: 5 Steps
10 min
1
Open & Frame
Set context, define each MoSCoW category, confirm scope.
10 min
2
Generate Items
Participants write one requirement or feature per sticky.
5 min
3
Brief Reads
Each participant reads items aloud. No discussion yet.
20–30 min
4
Categorize
Group places each item. Discuss conflicts. Dot-vote to resolve.
10 min
5
Finalize & Capture
Confirm Must Haves. Assign owners. Document decisions.
STEPHENS INSIGHT GROUP
stephensinsightgroup.com

## Slide 5
STEPS 1 & 2
Open the Session & Generate Items
STEP 1 — Open & Frame (10 min)
Welcome participants and explain the purpose of the session
Define each category with examples from the project context: Must Have, Should Have, Could Have, Won't Have
Confirm the scope boundary: What project, sprint, or initiative are we prioritizing for today?
Set expectations: Won't Have does not mean rejected — it means not this iteration
Announce the session length and how the final list will be documented and shared
STEP 2 — Generate Items (10 min)
Each participant writes requirements, features, or tasks — one item per sticky note
Keep items concise and action-oriented: "SSO login" rather than "Authentication considerations"
All items go to a neutral staging area — no filtering, grouping, or categorizing yet
Encourage completeness: if it's on anyone's mind, it belongs on the board
Virtual tip: set a visible countdown timer so everyone writes simultaneously and silently
STEPHENS INSIGHT GROUP
stephensinsightgroup.com

## Slide 6
STEPS 3 & 4
Item Introductions & Categorization
STEP 3 — Brief Reads (5 min)
Each participant reads their sticky notes aloud — 15–30 seconds per item
One or two sentences only: what the item is and why it matters to this project
No categorization at this stage — just enough context for the group to place it
Facilitator gently redirects any item introduction that turns into a full discussion
Cluster obvious duplicates on the staging board before categorization begins
STEP 4 — Categorize (20–30 min)
The group moves each item into one of the four MoSCoW columns as a team
Start with clear Must Haves — items the project truly cannot ship without
Work outward: Should Have → Could Have → Won't Have
For contested items: allow a 2-minute discussion, then dot-vote to resolve
Facilitator tracks time — no single item should consume the session
Break ties with: majority rules, sponsor's decision, or defer to next session
STEPHENS INSIGHT GROUP
stephensinsightgroup.com

## Slide 7
STEP 4 REFERENCE
The MoSCoW Prioritization Board
Every item belongs in one of four columns. Set this board up before participants arrive.
M
Must Have
Non-negotiable. Without these, the project fails or the release cannot ship.
If in doubt — it's NOT a Must Have
S
Should Have
Important and expected, but the project can survive a release without them.
Include if time & resources allow
C
Could Have
Desirable but not necessary. Dropped first when the team is under pressure.
Explore after Musts & Shoulds are set
W
Won't Have
Explicitly out of scope this iteration. Not a permanent no — revisit next cycle.
Prevents scope-creep arguments
STEPHENS INSIGHT GROUP
stephensinsightgroup.com

## Slide 8
CLOSING THE SESSION
Wrap-Up & Decision Capture (10 min)
1
Review the Must Have column as a group — confirm every item truly meets the definition: the project fails without it
2
Assign a clear owner and target date to every Must Have item — unowned requirements quietly slip through delivery
3
In-person: photograph the board before anyone leaves. Virtual: export and save to a shared location immediately
4
Note uncategorized or still-contested items — carry them into a follow-up session rather than rushing a decision
5
Confirm next steps: who translates the board into the backlog, and by when?
6
Send a written summary within 24 hours: the final four-column breakdown, key decisions, and open questions
STEPHENS INSIGHT GROUP
stephensinsightgroup.com

## Slide 9
FACILITATOR GUIDANCE
Anti-Patterns to Avoid
MoSCoW works best when the Facilitator maintains objectivity and guards the process. Watch for these common failure modes:
Everything Is a Must Have
Challenge with: "If this is a Must Have, what gets cut when we're over budget?" Use forced ranking or the 60% rule: Must Haves should not exceed 60% of effort.
HiPPO Effect
The Highest Paid Person's Opinion shouldn't override the group. Use anonymous dot voting or pre-session surveys to surface honest priorities.
Won't Have = Permanent Rejection
Reframe explicitly: "Won't Have means not this cycle." Document these items so the team can revisit them next sprint or quarter.
Scope Creep Mid-Session
New items raised during categorization go to a "parking lot." Review after the core list is placed — not inline.
Skipping the Brief Reads
Without shared context, items get miscategorized. Brief reads take 5 minutes and prevent hours of rework or misaligned delivery.
No Follow-Up Documentation
Without a written record sent within 24 hours, the decisions evaporate. Assign a Scribe before the session begins.
STEPHENS INSIGHT GROUP
stephensinsightgroup.com

## Slide 10
Ready to prioritize?
Trust the framework. Stay process-neutral.
The group will find clarity together.
Download the MoSCoW session template at stephensinsightgroup.com/moscow-workshop
STEPHENS INSIGHT GROUP
stephensinsightgroup.com