## Slide 1
WORKSHOP GUIDE
Capacity Planning
A facilitator's guide to helping a team calculate, protect, and communicate its true available capacity before each planning cycle.
Stephens Insight Group | Facilitator Presentation
Notes: Title slide. Open by introducing yourself and the purpose of the session.

## Slide 2
01 / WHY THIS MATTERS
What gets planned without a capacity number gets broken by reality
Teams that plan to 100% of headcount routinely miss. Capacity planning makes the real number visible before commitments are made.
1
Prevent Overcommitment
A defined capacity ceiling stops the team from accepting more work than it can realistically finish in a sprint.
2
Surface Hidden Constraints
Vacation, training, support rotation, and recurring Agile Events reduce availability more than people intuitively expect.
3
Build Planning Credibility
When leadership can see the math, they trust the plan — and stop asking the team to squeeze in more without removing something else.
Capacity Planning Workshop Guide
Notes: Give the team 2–3 minutes to discuss the last time their sprint commitment did not match reality. Use that as a bridge into the session.

## Slide 3
02 / SESSION AGENDA
Six steps from headcount to a usable capacity number
Work in order. Each step's output feeds the next. Skipping ahead produces a number nobody believes.
1
Identify Team Members
5 min
2
Set Sprint Parameters
5 min
3
Calculate Gross Capacity
10 min
4
Apply Deductions
15 min
5
Arrive at Net Capacity
5 min
6
Validate and Communicate
10 min
Capacity Planning Workshop Guide
Notes: Walk through the agenda briefly. Total run time is ~50 min with discussion. Ask if anyone has a hard stop before you begin.

## Slide 4
03 / FACILITATION — STEP 1 OF 6
Identify Team Members
Establish who is on the team and whether each person is fully allocated to this team for the sprint.
List every person who will be doing delivery work this sprint — developers, testers, designers, and analysts
Capture each person's allocation percentage if they split time across teams or programs
Exclude stakeholders, product owners, and scrum masters unless they also carry delivery work
Document names and allocations in the Capacity Planning Worksheet before moving on
FACILITATOR TIP
Ask: "Is anyone on this list also committed to another team or another program?" Unspoken split-allocations are the most common hidden constraint in capacity planning — they never appear unless you ask.
Capacity Planning Workshop Guide

## Slide 5
03 / FACILITATION — STEP 2 OF 6
Set Sprint Parameters
Agree on the sprint length and the productive hours per day that define the container for all capacity math.
Confirm the sprint length in business days — standard is 10 days for a two-week sprint
Define productive hours per person per day — typically 6 to 6.5 hours, not 8, to account for overhead
Record sprint start and end dates so deductions can be tied to specific calendar days
If the sprint length varies, agree on a standard rule now and apply it consistently going forward
FACILITATOR TIP
Teams that use 8 hours per day consistently overcommit. Build in overhead (stand-ups, email, context-switching) by defaulting to 6 hours. The team can adjust this assumption after one or two sprints of data.
Capacity Planning Workshop Guide

## Slide 6
03 / FACILITATION — STEP 3 OF 6
Calculate Gross Capacity
Multiply available days by hours per day per person to get the theoretical maximum before any deductions.
For each team member: sprint days × hours per day × allocation percentage = gross capacity in hours
Sum individual gross capacities to get the team total for the sprint
Display this number visibly — it is the ceiling against which all deductions will be subtracted
Use the Capacity Planning Worksheet to capture and share the math live with the team as you go
FACILITATOR TIP
Show the gross number explicitly before starting deductions. Watching it shrink in real time helps the team internalize why commitment ceilings exist — the reveal is part of the value of running this together.
Capacity Planning Workshop Guide

## Slide 7
03 / FACILITATION — STEP 4 OF 6
Apply Deductions
Subtract every known constraint: vacation, holidays, Agile Events, support rotation, and training.
Vacation and personal time off: confirm days for each person; convert to hours using the sprint's hours-per-day rate
Company holidays: apply only the holidays that fall inside the sprint window
Recurring Agile Events: Sprint Planning, Review, Retrospective, and Backlog Refinement hours for all team members
Training, conferences, onboarding obligations, and any standing support or oncall rotation shifts
FACILITATOR TIP
Pre-calculate Agile Event hours before the workshop using standard meeting lengths and present them as a given. Don't debate the size of overhead deductions during the session — the team can tune them in a future retrospective if the number feels wrong.
Capacity Planning Workshop Guide

## Slide 8
03 / FACILITATION — STEP 5 OF 6
Arrive at Net Capacity
Subtract total deductions from gross capacity to produce the number the team will plan against.
Net Capacity = Gross Capacity minus all deductions, expressed in hours
Convert to story points if the team plans in points using the team's established hours-per-point ratio
If the number surprises anyone, surface the concern now — revisit and adjust deductions before locking the figure
Record net capacity in the worksheet and confirm it with the full team before moving to planning
FACILITATOR TIP
If net capacity falls below 60% of gross, the team likely has a structural constraint — chronic overhead, a heavy support load, or endemic split allocation. Surface this to leadership as a planning risk, not a team performance problem.
Capacity Planning Workshop Guide

## Slide 9
03 / FACILITATION — STEP 6 OF 6
Validate and Communicate
Sanity-check the number against recent history and share it with stakeholders before planning begins.
Compare net capacity to the last two or three sprints' actual velocity — significant divergence means revisiting your deductions
Share the completed worksheet with the Product Owner and relevant stakeholders before Sprint or PI Planning
Note any factors that make this sprint unusual: post-holiday recovery, a new team member ramping, a release crunch
Commit to re-running the calculation each sprint — capacity changes every cycle and estimates drift without it
FACILITATOR TIP
"Why is the capacity so low?" is the most common stakeholder objection. Walk them through the deduction list line by line. A number with visible math is always more persuasive than a number without it.
Capacity Planning Workshop Guide

## Slide 10
04 / EXPECTED OUTPUTS
What the team walks away with
A successful capacity planning session leaves the team with three things: a number, a record, and a shared understanding.
1
Net Capacity in Hours
A defensible, math-backed capacity ceiling for the upcoming sprint or PI — ready to share with planning stakeholders.
2
Completed Worksheet
A filled-in Capacity Planning Worksheet showing every team member's availability and every deduction applied — auditable at any point.
3
A Repeatable Cadence
Agreement on when and how capacity will be calculated for every future sprint — not a one-time exercise done before a big release.
Capacity Planning Workshop Guide
Notes: Review the three outputs with the team. Ask which one they are most likely to skip and make a plan to prevent it.

## Slide 11
05 / AFTER THE WORKSHOP
Keep it visible, keep it honest
A capacity number filed away immediately stops being useful. Put it in front of the team and leave it there.
Post the completed worksheet in the team's shared planning space (Confluence, SharePoint, or equivalent)
Reference the net capacity number explicitly when accepting sprint or PI commitments
Revisit actual vs. planned capacity in the sprint retrospective — it is the fastest way to calibrate the model
Identify one person to own the capacity calculation each cycle — rotate the responsibility across the team
Schedule the next capacity planning session before this one ends
Stephens Insight Group | stephensinsightgroup.com | info@stephensinsightgroup.com
Notes: Closing slide. Remind the team to schedule the next capacity planning session before they leave. Leave time for questions.