## Instructions
SIG Capacity Planning Worksheet
Stephens Insight Group — Capacity Planning Workshop
How this workbook is organized
Team Capacity | Enter each team member's available sprint days for the PI and planned deductions (PTO, holidays, training, part-time availability). The sheet calculates net available days and applies a realistic load factor.
Velocity & Throughput | Enter each team's velocity from the last three sprints. The sheet averages velocity and translates adjusted capacity into an estimated PI throughput in story points.
ART Capacity Rollup | Aggregates adjusted capacity and estimated throughput across all teams into a single Agile Release Train (ART) view.
Demand vs Capacity | List the prioritized feature/epic backlog from Product Management. The sheet tracks cumulative point consumption against ART capacity and flags each item Committed or Parking Lot.
Parking Lot | Copy any item marked "Parking Lot" on the Demand vs Capacity tab here, along with the business impact of deferring it, for discussion in the Identify Gaps and Explore Options step.
Editing guide
Blue text | Cells you fill in (inputs).
Black text | Formulas — do not overwrite; they recalculate automatically.
Yellow fill | Key assumptions to confirm before the session (e.g., load factor, sprints per PI).
Capacity formula used | Adjusted Capacity Days = (Sprint Days Available - Planned Deductions) x Load Factor
Recommended load factor | 70-80% of theoretical capacity, per SIG facilitation guidance, to account for meetings, overhead, and unplanned work.

## Team Capacity
Team Capacity
Fill in one row per team member. Sprint Days Available and Planned Deductions are for the full PI (all sprints combined).
Team | Team Member | Role | Sprint Days Available (PI) | Planned Deductions (days) | Net Available Days | Load Factor | Adjusted Capacity Days
Team Falcon | Alex Rivera | Developer | 50 | 5 | 45 | 75% | 33.75
Team Falcon | Jamie Chen | Developer | 50 | 10 | 40 | 75% | 30
Team Falcon | Morgan Lee | QA Engineer | 50 | 0 | 50 | 75% | 37.5
Team Osprey | Taylor Brooks | Developer | 50 | 15 | 35 | 75% | 26.25
Team Osprey | Sam Patel | Developer | 50 | 0 | 50 | 75% | 37.5
Team Subtotals
Team | Sprint Days Available (PI) | Planned Deductions (days) | Net Available Days | Adjusted Capacity Days
Team Falcon | 150 | 15 | 135 | 101.25
Team Osprey | 100 | 15 | 85 | 63.75

## Velocity & Throughput
Velocity & Throughput
Enter each team's velocity (story points) from the last three sprints, and confirm sprints per PI.
Team | Sprint N-2 | Sprint N-1 | Sprint N (last) | Avg Velocity / Sprint | Sprints per PI | Adjusted Capacity Days | Planned Capacity Days | Estimated PI Throughput (pts)
Team Falcon | 28 | 31 | 30 | 29.6667 | 5 | 101.25 | 150 | 100.125
Team Osprey | 22 | 20 | 24 | 22 | 5 | 63.75 | 100 | 70.125

## ART Capacity Rollup
ART Capacity Rollup
Aggregated view across all teams for this Agile Release Train (ART) or Program Increment (PI).
Team | Adjusted Capacity Days | Estimated PI Throughput (pts)
Team Falcon | 101.25 | 100.125
Team Osprey | 63.75 | 70.125
ART Total | 165 | 170.25

## Demand vs Capacity
Demand vs Capacity
List the prioritized feature/epic backlog from Product Management, ranked highest priority first. Items are mapped against ART capacity in rank order.
Rank | Feature / Epic | Team | Estimated Size (pts) | Cumulative Points | ART Capacity (pts) | Status
1 | Real-time inventory sync | Team Falcon | 13 | 13 | 170.25 | Committed
2 | Customer self-service portal | Team Osprey | 21 | 34 | 170.25 | Committed
3 | Automated invoice reconciliation | Team Falcon | 8 | 42 | 170.25 | Committed
4 | Mobile checkout redesign | Team Osprey | 34 | 76 | 170.25 | Committed
5 | Partner API rate limiting | Team Falcon | 13 | 89 | 170.25 | Committed
Items marked "Parking Lot" exceed available ART capacity. Copy them to the Parking Lot tab for discussion.

## Parking Lot
Parking Lot
Copy items marked "Parking Lot" from the Demand vs Capacity tab. Capture the business impact of deferring each item and any escalation owner.
Feature / Epic | Estimated Size (pts) | Business Impact of Deferring | Escalation Owner