## Slide 1
WORKSHOP GUIDE
WSJF Workshop
A facilitator's guide to helping a team prioritize work by sequencing the highest economic value first.
Stephens Insight Group | Facilitator Presentation

## Slide 2
00 / OVERVIEW
Agenda
Topics covered in this facilitator session.
1
Introduction to WSJF
2
When to Use
3
Cost of Delay
4
Job Size Estimation
5
Example Scenario
6
WSJF Scoring Template
7
Let's WSJF!
8
Q & A
WSJF Workshop Guide

## Slide 3
01 / INTRODUCTION
Introduction to WSJF
WSJF noun: (wis-jif); a prioritization model that sequences work to deliver maximum economic value first.
Core Principle
Don't just rank by business value — factor in urgency, risk, and how long the job will take. The smallest, most urgent jobs often deliver the highest economic value fastest.
The Formula
WSJF = Cost of Delay ÷ Job Size
Cost of Delay captures what the business loses by waiting. Job Size normalizes it by effort.
Why It Works
By dividing urgency and value by how long the work takes, WSJF naturally surfaces small, high-impact items that would otherwise wait behind larger — but equally valuable — initiatives.
WSJF Workshop Guide

## Slide 4
01 / INTRODUCTION
When to Use
WSJF is most valuable when the team exhibits one or more of these signals.
Long Backlog, No Clear Order
The team has more features than capacity and can't agree objectively on what to build next.
Competing Stakeholder Priorities
Different business owners each believe their item is the most important — WSJF gives the team a shared, data-driven language.
Large Batches Getting Priority
Big initiatives are consuming all capacity while smaller, high-value items sit waiting with no path forward.
Preparing for PI Planning
The team needs an objective way to sequence features before committing to a Program Increment.
WSJF Workshop Guide

## Slide 5
02 / THE WSJF FORMULA
The WSJF Formula
Components & Calculation

## Slide 6
02 / THE WSJF FORMULA
Cost of Delay
Cost of Delay is the sum of three components — each scored on a relative Fibonacci scale: 1, 2, 3, 5, 8, 13, 20.
User-Business Value
How much do users and the business value this compared to other items?
Consider revenue generated, cost saved, customer satisfaction improved, or strategic alignment.
Time Criticality
How does the value decay over time?
Consider fixed deadlines, market windows, regulatory dates, or the cost of a delayed launch.
Risk Reduction |
Opportunity Enablement
Does this reduce a future risk or enable a future opportunity?
Consider technical debt, compliance exposure, or unlocking a dependent feature set.
WSJF Workshop Guide

## Slide 7
02 / THE WSJF FORMULA
Job Size
Job Size is the relative effort required — it represents duration, not complexity alone.
What It Is
Job Size is how long the work will occupy the team — relative to other items. Use the same Fibonacci scale: 1, 2, 3, 5, 8, 13, 20.
Key Rule
A Job Size of 1 represents the smallest, fastest item on the backlog. All others are sized relative to it.
FACILITATOR TIP
Job Size is NOT story points.
It represents calendar time or overall team effort — how long will this initiative actually occupy the team?
If two features have the same business value but one takes 13 weeks and the other takes 2, the shorter one should almost always go first.
WSJF Workshop Guide

## Slide 8
02 / THE WSJF FORMULA
Calculating WSJF
Follow these four steps during the scoring session.
1
Step 1: List Your Backlog Items
Identify the features or epics to be sequenced. Aim for 5–15 items for a productive session.
2
Step 2: Score Each Component
As a team, score User-Business Value, Time Criticality, and Risk Reduction | Opportunity Enablement for each item. Use dot voting or consensus.
3
Step 3: Calculate Cost of Delay
Add the three component scores: CoD = UBV + TC + RR/OE. This is your urgency numerator.
4
Step 4: Divide by Job Size
WSJF = Cost of Delay ÷ Job Size. Sort items by WSJF score — highest score = highest priority.
WSJF Workshop Guide

## Slide 9
03 / EXAMPLE SCENARIO
Example Scenario

## Slide 10
03 / EXAMPLE SCENARIO
WSJF Scoring Example
Your team has four features in the backlog. Score each one and determine which to build first.
1
Mobile App Login (SSO)
Users are requesting single sign-on. A compliance requirement is also approaching.
2
Compliance Reporting Dashboard
Regulators require monthly reports. Missed deadlines carry financial penalties.
3
Customer Portal Redesign
Modernize the UI. High user satisfaction impact but no hard deadline.
4
API Rate Limiting
Without this, a downstream service cannot launch. It is a blocker for the next release train.
WSJF Workshop Guide

## Slide 11
03 / EXAMPLE SCENARIO
Score the Backlog
The team has scored each feature. Calculate the WSJF for each item.
Feature
User-Business Value
Time Criticality
Risk Reduction | OE
Cost of Delay
Job Size
WSJF
Mobile App Login (SSO)
8
3
5
16
5
3.2
Compliance Reporting Dashboard
5
13
8
26
8
3.25
Customer Portal Redesign
13
2
2
17
13
1.31
API Rate Limiting
3
5
13
21
3
7.0
CoD = User-Business Value + Time Criticality + Risk Reduction | Opportunity Enablement | WSJF = CoD ÷ Job Size
WSJF Workshop Guide

## Slide 12
03 / EXAMPLE SCENARIO
Results: Prioritized Backlog
Sorted by WSJF score — highest score goes first.
1
API Rate Limiting
WSJF: 7.0
Highest WSJF. Small job (size 3) with high risk reduction (13). Build this first.
2
Compliance Reporting Dashboard
WSJF: 3.25
Strong time criticality (13) from regulatory deadline. Build next.
3
Mobile App Login (SSO)
WSJF: 3.2
High business value (8) with moderate urgency. Close behind #2.
4
Customer Portal Redesign
WSJF: 1.31
Highest user-business value (13) but large job size (13) and no urgency. Defer.
WSJF Workshop Guide

## Slide 13
03 / EXAMPLE SCENARIO
Spot the Insight
API Rate Limiting has a WSJF of 7.0 — despite its low user-business value score.
API Rate Limiting
User-Business Value: 3 | Time Criticality: 5 | Risk Reduction: 13 | CoD: 21 | Job Size: 3 | WSJF: 7.0
FACILITATOR TIP
Ask: "Why would we build something with a business value of 3 before something with a business value of 13?"
Let the team land on the answer: because its high risk reduction score and small job size combine to create a 7.0 WSJF — it unblocks the next release and takes very little time.
The Key Insight
A small, high-urgency job will almost always outrank a large, equally-valuable one.
This is the economic logic WSJF makes visible — and why teams that use it deliver value faster than teams that sequence by business value alone.
This is Lean Portfolio Management earning its value: exposing the hidden cost of waiting.
WSJF Workshop Guide

## Slide 14
03 / EXAMPLE SCENARIO
Discuss: Do You Agree?
As a group, review the prioritized sequence and discuss:
?
Does the scoring reflect your team's actual understanding of urgency and value?
?
Is there a feature whose score surprised you? Why?
?
Are there constraints or dependencies not captured by the scoring?
?
How confident are you in the Job Size estimates — could any of them shift the ranking?
Resolution: API Rate Limiting is the clear first priority — build it before starting any new features in the same domain.
WSJF Workshop Guide

## Slide 15
04 / TEMPLATE
WSJF Scoring Template

## Slide 16
04 / TEMPLATE
WSJF Scoring Template
Use this template to facilitate a scoring session with your team.
Scoring Rule: WSJF = (User-Business Value + Time Criticality + Risk Reduction | OE) ÷ Job Size | Use Fibonacci: 1, 2, 3, 5, 8, 13, 20
Epic / Feature
Owner / Value Stream
User-Business Value
Time Criticality
Risk Reduction | OE
Cost of Delay
Job Size
WSJF Score
Migrate Core Platform
Value Stream A
8
5
3
16
5
3.2
WSJF Workshop Guide

## Slide 17
04 / LET'S WSJF!
Questions?
Let's WSJF!
Stephens Insight Group | Facilitator Presentation