## Start Here
Benefits Realization Tracker
Prove the program delivered the value it promised ¦ SIG Template v1.0
Purpose | Turns the benefits in your business case into measures with owners, baselines and targets, then tracks actual results over time so you can show what the investment returned.
How to use | 1. Benefits Register: one row per benefit, with how it will be measured, the baseline, the target and the date it should be reached. Each benefit needs a business owner, not just the program team. 2. Measurements: add a row each time you measure a benefit. 3. Summary: the latest measurement, progress to target and status calculate for each benefit. 4. Closeout Review: use at program close and again after benefits have had time to land.
Progress to target | Progress = (latest actual - baseline) / (target - baseline). It works whether the goal is to increase or decrease a measure. Status: On track at 90% or more of the expected progress for the date, Behind below that, Achieved at 100% or more. The expected progress line assumes steady improvement from the start date to the target date; adjust if your benefits ramp differently.
Pairs with | SIG Business Case and TCO Template (the source of your benefit targets), SIG Executive Status Report, and SIG PI Progress and Milestone Report.
Cells with this fill are for you to complete
© 2026 Stephens Insight Group LLC. Capital In. Value Out. ¦ stephensinsightgroup.com

## Summary
Benefits Summary
Calculates from the Benefits Register and Measurements tabs. Do not type in this sheet.
As of date: | 2026-10-05
Benefit ID | Benefit | Owner | Baseline | Target | Latest actual | Latest date | Progress to target | Expected by now | Status
B-001 | EXAMPLE (delete): Faster month-end close |  | 10 | 6 | 9 | 0 | 25% |  | Tracking
Status: Achieved at 100% of target or more. On track when progress is at least 90% of where steady improvement would be by today. Behind below that.
© 2026 Stephens Insight Group LLC. Capital In. Value Out. ¦ stephensinsightgroup.com
Formulas:
Latest date = IF([Benefit ID]="","",IF(COUNTIF(Measurements!$A2:A61,[Benefit ID])=0,"",MAXIFS(Measurements!$B2:B61,Measurements!$A2:A61,[Benefit ID])))

## Benefits Register
Benefit ID | Benefit | Type | Measure | Unit | Baseline | Target | Start date | Target date | Business owner | Business case line | How measured | Frequency
B-001 | EXAMPLE (delete): Faster month-end close | Efficiency | Business days to close the books | days | 10 | 6 |  |  |  |  | Finance close calendar | Monthly
B-002
B-003
B-004
B-005
B-006
B-007
B-008
B-009
B-010
B-011
B-012
B-013
B-014
B-015
B-016
B-017
B-018
B-019
B-020

## Measurements
Benefit ID | Measurement date | Actual value | Source | Notes
B-001 |  | 9 | Finance close calendar | EXAMPLE (delete) first month after go-live

## Closeout Review
Benefits Closeout Review
Complete at program closeout, then again once benefits have had time to land.
Question | Response
Review date and participants
Which benefits were achieved, and what evidence shows it?
Which benefits fell short, and why?
Were any benefits we did not plan for realized?
What costs or side effects did we not expect?
Who owns each benefit still being tracked after closeout?
When is the next benefits review?
What should future business cases do differently?
Sponsor sign-off (name and date)