## Start Here
Change Communication Plan
Who needs to hear what, from whom, and when ¦ SIG Template v1.0
Purpose | Plans every communication about a change: who the audiences are, the key messages, the calendar of what goes out when, and the feedback that comes back. Works for any program, release or organizational change.
How to use | 1. Audience Analysis: confirm the audiences and fill in what each one cares about. 2. Key Messages: write and approve the core messages once, then reuse them. 3. Communication Calendar: schedule each communication against releases and milestones. 4. Feedback Log: capture questions and concerns, and close the loop.
Preloaded content | Audience types, message themes and a typical sequence of communications are preloaded as a starting point. Rename, delete or add rows to fit your change. Dates and owners are left blank.
Good practice | Have the sponsor explain why the change is happening, and have each person's own manager explain what it means for their team. Send important messages more than once and through more than one channel. Ask for feedback on every communication, and show people what you did with it.
Pairs with | SIG Stakeholder and Change Impact Tracker, SIG Training and Readiness Plan, and the SIG Program Management Toolkit (Governance Charter and RACI, RAID Log).
Cells with this fill are for you to complete
© 2026 Stephens Insight Group LLC. Capital In. Value Out. ¦ stephensinsightgroup.com

## Audience Analysis
Audience | Who is in it | What they usually care about | What changes for them | Influence (H/M/L) | Preferred channels | Best messenger | Notes
Executive sponsor and steering committee |  | Progress, risks, decisions they need to make
Senior leadership |  | Business outcomes, timing, impact on their area
People managers |  | What changes for their team, what they need to do, how to answer questions
Directly impacted users |  | What changes for me, when, training, where to get help
Indirectly impacted teams |  | Handoffs, dependencies, anything they need to adjust
Delivery teams and partners |  | Plans, decisions, dates, how their work fits
Support and help desk |  | What is changing, expected questions, escalation path
Customers or external partners |  | What they will notice, when, who to contact

## Key Messages
Message ID | Theme | Guidance | Core message (1 to 2 sentences) | Supporting points | Approved by | Date approved
M-001 | Why we are changing | The business reason and what happens if we do not change
M-002 | What is changing | The scope in plain language: what is new, what stays the same, what goes away
M-003 | When it happens | Key dates, releases and what to expect at each one
M-004 | What it means for me | Impact by audience; written with or by people managers
M-005 | How we will support you | Training, job aids, office hours and where to get help
M-006 | How to give feedback | Where to send questions and how answers will be shared
M-007
M-008
M-009
M-010
M-011
M-012

## Communication Calendar
Comm ID | Communication | Audience | Message theme | Channel | Sender / messenger | Owner | Timing or milestone | Planned date | Frequency | Status | Feedback captured?
C-001 | Program announcement | All impacted audiences | Why we are changing | Email + town hall | Executive sponsor |  | Program kickoff |  |  | Planned
C-002 | Manager briefing pack | People managers | What it means for me | Team meeting + briefing deck | Program manager |  | Before announcement reaches teams |  |  | Planned
C-003 | Steering committee update | Executive sponsor and steering committee | What is changing | Status report | Program manager |  | Monthly |  |  | Planned
C-004 | Release preview or demo | Directly impacted users | What is changing | System Demo or recorded walkthrough | Product manager |  | Each release |  |  | Planned
C-005 | Training invitation | Directly impacted users | How we will support you | Email + calendar invite | Change management lead |  | 3 to 4 weeks before go-live |  |  | Planned
C-006 | Go-live notice | All impacted audiences | When it happens | Email + intranet | Executive sponsor |  | 1 week before go-live |  |  | Planned
C-007 | Support briefing | Support and help desk | How we will support you | Briefing + knowledge articles | Delivery lead |  | Before go-live |  |  | Planned
C-008 | Go-live day message | Directly impacted users | How we will support you | Email + chat | Change management lead |  | Go-live day |  |  | Planned
C-009 | Post go-live check-in | Directly impacted users | How to give feedback | Survey + team meetings | Change management lead |  | 2 weeks after go-live |  |  | Planned
C-010 | Results and thank you | All impacted audiences | Why we are changing | Email + town hall | Executive sponsor |  | Program closeout |  |  | Planned
C-011
C-012
C-013
C-014
C-015
C-016
C-017
C-018
C-019
C-020
C-021
C-022
C-023
C-024
C-025

## Feedback Log
ID | Date | Audience | Channel | Question or feedback | Theme | Response given | Owner | Status | Shared back?
F-001 |  |  |  | EXAMPLE (delete): Will we still be able to run the old report after go-live? | What it means for me | Yes, for 30 days in read-only mode; a replacement report is covered in training. |  | Answered | Yes
F-002
F-003
F-004
F-005
F-006
F-007
F-008
F-009
F-010
F-011
F-012
F-013
F-014
F-015
F-016
F-017
F-018
F-019
F-020
F-021