## Start Here
Change Workbook
Stakeholders, change impacts, communications, training and go-live readiness in one file ¦ SIG Template v1.3
Quick start | 1. Change Impacts and Stakeholders: list each impacted group and key person, then rate impact and readiness from 1 to 5. 2. Key Messages, Comms Calendar and Feedback Log: agree the core messages, schedule who hears what and when, and close the loop on questions. 3. Training and Go-Live Checklist: plan training by group and track sessions, then use the checklist and Readiness Summary at your Go/No-Go.
Ratings | Impact: 4 or 5 = High (new way of working), 3 = Medium, 1 or 2 = Low. Readiness: 1 = Not aware, 2 = Aware, 3 = Preparing, 4 = Mostly ready, 5 = Ready. A row is flagged At risk when impact is High and readiness is 2 or lower.
Example | Accounts payable team, Process change: invoices move from email approval to the new workflow tool. Impact 5 and readiness 2, so the row is flagged At risk and gets hands-on training, a job aid and floor support.
Legend | Cells with this fill are for you to complete
© 2026 Stephens Insight Group LLC. Capital In. Value Out. ¦ stephensinsightgroup.com

## Change Impacts
ID | Impacted group | Headcount | Change area | Current state | Future state | Release / go-live | Impact (1-5) | Impact level | Readiness (1-5) | Readiness level | Flag | Change champion | Mitigation / support actions | Owner | Status

## Stakeholders
Name | Role / title | Group | Influence (H/L) | Impact on them (H/L) | Quadrant | Current stance | Desired stance | Engagement actions | Owner | Next touchpoint | Notes

## Readiness Summary
Readiness Summary by Group
Pick each impacted group from the dropdown (it lists the groups on Change Impacts). Everything else calculates. Use this view at your Go/No-Go.
Impacted group | Impact rows | High impact rows | Average readiness (1-5) | At Risk rows | Overall
© 2026 Stephens Insight Group LLC. Capital In. Value Out. ¦ stephensinsightgroup.com

## Key Messages
Message ID | Theme | Guidance | Core message (1 to 2 sentences) | Supporting points | Approved by | Date approved
| Why we are changing | The business reason and what happens if we do not change
| What is changing | The scope in plain language: what is new, what stays the same, what goes away
| When it happens | Key dates, releases and what to expect at each one
| What it means for me | Impact by audience; written with or by people managers
| How we will support you | Training, job aids, office hours and where to get help
| How to give feedback | Where to send questions and how answers will be shared

## Comms Calendar
Comm ID | Communication | Audience | Message theme | Channel | Sender / messenger | Owner | Timing or milestone | Planned date | Frequency | Status | Feedback captured?
| Program announcement | All impacted audiences | Why we are changing | Email + town hall | Executive sponsor |  | Program kickoff |  |  | Planned
| Manager briefing pack | People managers | What it means for me | Team meeting + briefing deck | Program manager |  | Before announcement reaches teams |  |  | Planned
| Steering committee update | Executive sponsor and steering committee | What is changing | Status report | Program manager |  | Monthly |  |  | Planned
| Release preview or demo | Directly impacted users | What is changing | System Demo or recorded walkthrough | Product manager |  | Each release |  |  | Planned
| Training invitation | Directly impacted users | How we will support you | Email + calendar invite | Change management lead |  | 3 to 4 weeks before go-live |  |  | Planned
| Go-live notice | All impacted audiences | When it happens | Email + intranet | Executive sponsor |  | 1 week before go-live |  |  | Planned
| Support briefing | Support and help desk | How we will support you | Briefing + knowledge articles | Delivery lead |  | Before go-live |  |  | Planned
| Go-live day message | Directly impacted users | How we will support you | Email + chat | Change management lead |  | Go-live day |  |  | Planned
| Post go-live check-in | Directly impacted users | How to give feedback | Survey + team meetings | Change management lead |  | 2 weeks after go-live |  |  | Planned
| Results and thank you | All impacted audiences | Why we are changing | Email + town hall | Executive sponsor |  | Program closeout |  |  | Planned

## Feedback Log
ID | Date | Audience | Channel | Question or feedback | Theme | Response given | Owner | Status | Shared back?

## Training
Training needs: one row per role or group
Role or group | Headcount | What they need to be able to do | Skill gap (H/M/L) | Training format | Content owner | Duration (hours) | Needed by (release) | Status | Notes
Training sessions: one row per session
Session ID | Course or topic | Audience | Format | Trainer | Date | Time | Location or link | Capacity | Registered | Attended | Attendance % | Status

## Go-Live Checklist
Go-Live Readiness Checklist
Release / go-live: |  |  | Complete:
Category | Readiness item | Owner | Due date | Status | Evidence or notes
People | Every impacted group has been identified and assigned an owner |  |  | Not started
People | Required training delivered and attendance meets target |  |  | Not started
People | People managers briefed and able to answer team questions |  |  | Not started
People | Change champions in place for each major group |  |  | Not started
Process | New or changed procedures documented and published |  |  | Not started
Process | Job aids and quick reference guides available |  |  | Not started
Process | Retired processes clearly communicated with an end date |  |  | Not started
Technology | User access and permissions set up and tested |  |  | Not started
Technology | Testing and UAT signed off by business owners |  |  | Not started
Technology | Rollback or contingency plan approved |  |  | Not started
Support | Help desk briefed with knowledge articles and escalation path |  |  | Not started
Support | Floor support or office hours scheduled for go-live week |  |  | Not started
Support | Issue tracking and triage process ready |  |  | Not started
Communications | Go-live notice sent to all impacted audiences |  |  | Not started
Communications | Where to get help is published and easy to find |  |  | Not started
Communications | Feedback channel open and monitored |  |  | Not started
Governance | Readiness Summary reviewed with business owners |  |  | Not started
Governance | Go/No-Go meeting scheduled with decision-makers |  |  | Not started