## Start Here
Data Governance WSJF Prioritization
Decide which governance work to do first ¦ SIG Template v1.3
Quick start | 1. Review the 14 starter initiatives; delete what does not apply and add your own. 2. Score one column at a time across all items: give the smallest item a 1, then score the rest relative to it using only 1, 2, 3, 5, 8, 13 or 20. Score as a group; Job Size is relative effort, not hours. 3. Read the Rank column: the highest WSJF goes first. Revisit scores when priorities or deadlines change.
How it works | Cost of Delay = Business Value + Time Criticality + Risk Reduction / Opportunity Enablement. WSJF = Cost of Delay / Job Size. See the SIG WSJF Workshop guide on stephensinsightgroup.com for facilitation steps.
Legend | Cells with this fill are for you to complete
© 2026 Stephens Insight Group LLC. Capital In. Value Out. ¦ stephensinsightgroup.com

## WSJF Calculator
ID | Initiative | Business Value | Time Criticality | Risk Reduction / Opportunity | Job Size | Cost of Delay | WSJF | Rank | Owner | Notes | Scale: 1, 2, 3, 5, 8, 13, 20
Name an executive sponsor and charter the governance program
Stand up a data governance council
Define data ownership and stewardship roles
Build a business glossary for the top critical terms
Identify critical data elements
Set data quality rules for critical data
Create a data issue intake and resolution process
Publish a data classification and handling policy
Standardize the data access request process
Pilot a data catalog or metadata inventory
Define data retention and archiving standards
Train data owners and stewards
Define governance success measures
Set up reference and master data ownership