## Start Here
PI Progress and Milestone Report
Track milestones, PI objectives and delivery progress in one place ¦ SIG Template v1.0
Purpose | Shows whether the program is delivering what it planned: milestones against baseline, PI objectives and predictability, Feature progress, and a burn-up of planned versus completed work.
How to use | 1. Milestones: enter baseline and forecast dates; variance and status calculate. 2. PI Objectives: after PI Planning, enter each team's objectives and planned business value (1 to 10). At the end of the PI, Business Owners score actual value. 3. Features: track each Feature's status and progress. 4. Burn-up: enter planned and completed points by iteration; the chart updates. 5. Summary: the headline numbers for your status report calculate from the other tabs.
PI predictability | Predictability = actual business value achieved / planned business value, for committed objectives only. Uncommitted (stretch) objectives can add to actual value but do not count in planned value. Many SAFe programs aim for 80% to 100%; agree your own target.
Milestone status | On time: forecast is on or before baseline. At risk: forecast slips by up to the tolerance on the Summary tab. Late: slips by more than the tolerance. Done: an actual date is entered.
Pairs with | SIG Executive Status Report, SIG Benefits Realization Tracker, and the SIG Program Jira Accelerator.
Cells with this fill are for you to complete
© 2026 Stephens Insight Group LLC. Capital In. Value Out. ¦ stephensinsightgroup.com

## Summary
PI Progress Summary
Headline numbers for your status report. Only the yellow cells are inputs.
Current PI
Milestone slip tolerance (days) | 10 | SIG starting point; set to your charter's schedule tolerance
Milestones: done | 0
Milestones: on time | 0
Milestones: at risk | 0
Milestones: late | 0
PI predictability (current PI) |  | Actual value of all objectives / planned value of committed objectives
Committed objectives (current PI) | 0
Features done | 0
Features in progress | 0
Features blocked | 0
Points done / planned
© 2026 Stephens Insight Group LLC. Capital In. Value Out. ¦ stephensinsightgroup.com

## Milestones
ID | Milestone | Owner | Baseline date | Forecast date | Actual date | Variance (days) | Status | Notes
MS-001
MS-002
MS-003
MS-004
MS-005
MS-006
MS-007
MS-008
MS-009
MS-010
MS-011
MS-012
MS-013
MS-014
MS-015
MS-016
MS-017
MS-018
MS-019
MS-020
MS-021
MS-022
MS-023
MS-024
MS-025

## PI Objectives
PI | Team | Objective | Committed? | Planned value (1-10) | Actual value (1-10) | Achieved % | Business owner notes

## Features
Feature | Epic | Team | Target PI | Status | % complete | Points planned | Points done | Blocked? | Notes

## Burn-up
Iteration | Planned points | Completed points | Cumulative planned | Cumulative completed
Iteration 1
Iteration 2
Iteration 3
Iteration 4
Iteration 5
Iteration 6
Iteration 7
Iteration 8
Iteration 9
Iteration 10
Iteration 11
Iteration 12
Fill in iterations as they finish; future iterations stay blank on the chart.