## Start Here
PI Progress and Milestone Report
Track milestones, PI objectives and delivery progress in one place ¦ SIG Template v1.3
Quick start | 1. Milestones: enter baseline and forecast dates; variance and status calculate. 2. PI Objectives: after PI Planning, enter each team’s objectives and planned business value (1 to 10); Business Owners score actual value at the end of the PI. 3. Summary: set the current PI, then enter burn-up points by iteration. Headline numbers and the chart update for your status report.
Good to know | Milestone status: On time if the forecast is on or before baseline, At risk if it slips by up to the tolerance on Summary, Late beyond that, Done once an actual date is entered. Predictability = actual business value / planned value of committed objectives. Feature-level progress lives in Jira.
Legend | Cells with this fill are for you to complete
© 2026 Stephens Insight Group LLC. Capital In. Value Out. ¦ stephensinsightgroup.com

## Summary
PI Progress Summary
Headline numbers for your status report. Only the yellow cells are inputs.
Current PI
Milestone slip tolerance (days) |  | 10 | SIG starting point; set to your charter's schedule tolerance
Milestones: done
Milestones: on time
Milestones: at risk
Milestones: late
PI predictability (current PI) |  |  | Actual value of all objectives / planned value of committed objectives
Committed objectives (current PI)
Burn-up (enter points as each iteration finishes)
Iteration | Planned points | Completed points | Cumulative planned | Cumulative completed
Iteration 1
Iteration 2
Iteration 3
Iteration 4
Iteration 5
Iteration 6
Iteration 7
Iteration 8
Iteration 9
Iteration 10
Iteration 11
Iteration 12
© 2026 Stephens Insight Group LLC. Capital In. Value Out. ¦ stephensinsightgroup.com

## Milestones
ID | Milestone | Owner | Baseline date | Forecast date | Actual date | Variance (days) | Status | Notes

## PI Objectives
PI | Team | Objective | Committed? | Planned value (1-10) | Actual value (1-10) | Achieved % | Business owner notes