## Start Here
Program Jira Accelerator
Program and project management backlog for any large initiative ¦ SIG Accelerator v1.0
What this is | A ready-to-import backlog of Epics, Features and Stories covering the program and project management work every large initiative needs: mobilization, governance, discovery, decisions, readiness, release planning, acceptance, change management and closeout. Delivery teams add their own technical Stories under each Feature.
Contents | 8 Epics, 23 Features, 75 Stories.
Tabs | Backlog View: readable hierarchy with hypotheses and acceptance criteria, plus Owner, PI and Status columns to fill in. Jira Import: flat table that matches the companion CSV file.
How to import | 1. Tailor the Backlog View first: remove what is out of scope, rename releases, and add program-specific items. 2. In Jira, go to the CSV importer (System > External System Import > CSV, or the project's Import issues option). 3. Map columns: Issue ID > Issue Id, Parent ID > Parent Id, Issue Type, Summary, Description, Labels. Map Epic Name only if your Jira asks for it. 4. Import Epics first if your Jira version requires parents to exist before children.
If you have no 'Feature' type | Many Jira setups use Epic > Story only. Options: (a) map Feature rows to Epic and Epic rows to a higher level type such as Initiative, or (b) import Features as Epics and keep the SIG Epic name as a label. Confirm with your Jira administrator.
Release N | The 'Release N delivered' Feature is a template. Copy it once per release on your roadmap.
Pairs with | SIG Business Case and TCO Template, SIG Governance Charter and RACI, SIG Program RAID Log, and the SIG Strategic Themes, SIPOC and WSJF workshop guides.
© 2026 Stephens Insight Group LLC. Capital In. Value Out. ¦ stephensinsightgroup.com

## Backlog View
ID | Level | Parent ID | Phase | Summary | Hypothesis | Acceptance Criteria | Owner | Target PI | Status
1 | Epic |  | Phase 0 Mobilize | Program Mobilization and Strategic Alignment | If we secure a clear executive imperative, governance and an approved business case before delivery begins, then the program will make faster decisions and avoid rework caused by shifting priorities. |  |  |  | Not Started
2 | Feature | 1 | Phase 0 Mobilize | Executive imperative and Strategic Themes defined | A written imperative and Strategic Themes give every team the same answer to 'why are we doing this'. | Strategic Themes and OKRs approved by the executive sponsor and published to the program team. |  |  | Not Started
3 | Story | 2 | Phase 0 Mobilize | Confirm executive sponsor and named decision-maker(s) |  | Sponsor and decision-makers are named in the governance charter and have accepted the role. |  |  | Not Started
4 | Story | 2 | Phase 0 Mobilize | Facilitate Strategic Themes workshop for the program |  | Workshop held with business, technology and operations leaders; 2 to 4 themes drafted. |  |  | Not Started
5 | Story | 2 | Phase 0 Mobilize | Draft program OKRs aligned to Strategic Themes |  | Each theme has at least one Objective with measurable Key Results and an owner. |  |  | Not Started
6 | Story | 2 | Phase 0 Mobilize | Identify hard date constraints (contract renewals, regulatory or fiscal deadlines) |  | Constraint dates confirmed with their owners and logged as milestones and dependencies in the RAID log. |  |  | Not Started
7 | Feature | 1 | Phase 0 Mobilize | Program governance established | Defined decision rights and cadence reduce decision latency and escalations. | Governance charter and RACI signed off; steering committee calendar issued; RAID log live. |  |  | Not Started
8 | Story | 7 | Phase 0 Mobilize | Draft governance charter |  | Charter covers purpose, scope, decision rights, escalation path and meeting cadence. |  |  | Not Started
9 | Story | 7 | Phase 0 Mobilize | Build and validate program RACI |  | RACI reviewed with each accountable leader; exactly one Accountable per activity. |  |  | Not Started
10 | Story | 7 | Phase 0 Mobilize | Schedule steering committee and SAFe Events cadence |  | Recurring invitations sent for steering committee, PI Planning, System Demos and Inspect and Adapt. |  |  | Not Started
11 | Story | 7 | Phase 0 Mobilize | Stand up RAID log and review cadence |  | RAID log published; owners assigned; weekly review scheduled. |  |  | Not Started
12 | Feature | 1 | Phase 0 Mobilize | Program business case approved | A defensible business case secures funding and sets the benefits we will measure at closeout. | Business case reviewed by Finance and the Portfolio; Go decision recorded in the Portfolio Kanban. |  |  | Not Started
13 | Story | 12 | Phase 0 Mobilize | Collect current-state cost baseline |  | Current costs documented by line with Finance or the cost owner as the source. |  |  | Not Started
14 | Story | 12 | Phase 0 Mobilize | Collect future-state and one-time cost estimates |  | Estimates documented with assumptions and source for each line. |  |  | Not Started
15 | Story | 12 | Phase 0 Mobilize | Complete Business Case and TCO template |  | All input cells completed; summary reviewed by Finance. |  |  | Not Started
16 | Story | 12 | Phase 0 Mobilize | Present Epic to Lean Portfolio Management for Go/No-Go |  | Decision and conditions recorded on the Epic. |  |  | Not Started
17 | Feature | 1 | Phase 0 Mobilize | Program backlog and tooling ready | A ready backlog and shared tooling let teams start delivering in the first PI. | Jira project configured, accelerator imported, Definition of Ready and Done published. |  |  | Not Started
18 | Story | 17 | Phase 0 Mobilize | Configure Jira project, issue hierarchy and workflows |  | Epic, Feature and Story types available; workflow statuses agreed. |  |  | Not Started
19 | Story | 17 | Phase 0 Mobilize | Import and tailor the Program Jira Accelerator |  | Items imported; out-of-scope items closed with a reason; owners assigned. |  |  | Not Started
20 | Story | 17 | Phase 0 Mobilize | Publish Definition of Ready and Definition of Done |  | DoR and DoD reviewed with team leads and posted in the team space. |  |  | Not Started
21 | Story | 17 | Phase 0 Mobilize | Build program status dashboard |  | Dashboard shows Feature progress, milestones and top risks; shared with steering committee. |  |  | Not Started
22 | Epic |  | Phase 1 Discover | Discovery and Current State Assessment | If we understand the current state, who is affected and what they need, then we will scope the right work and avoid surprises at go-live. |  |  |  | Not Started
23 | Feature | 22 | Phase 1 Discover | Current state baseline documented | A clear baseline lets us measure improvement and spot what can be retired. | Current processes, systems, costs and performance measures documented and validated by their owners. |  |  | Not Started
24 | Story | 23 | Phase 1 Discover | Document current processes and workflows in scope |  | Process maps reviewed with process owners. |  |  | Not Started
25 | Story | 23 | Phase 1 Discover | Inventory systems, tools and assets in scope |  | Inventory lists owner, usage and criticality for each item. |  |  | Not Started
26 | Story | 23 | Phase 1 Discover | Capture baseline performance measures |  | Baseline values recorded with source and date for each measure to be tracked. |  |  | Not Started
27 | Story | 23 | Phase 1 Discover | Agree what will be kept, changed or retired |  | Disposition reviewed and accepted by owners. |  |  | Not Started
28 | Feature | 22 | Phase 1 Discover | Stakeholder and impact map | Mapping everyone affected early prevents missed stakeholders and broken handoffs. | Impact map published showing suppliers, inputs, process, outputs and customers, with impacted teams named. |  |  | Not Started
29 | Story | 28 | Phase 1 Discover | Facilitate SIPOC workshop for the program scope |  | SIPOC completed and validated with supplier and customer representatives. |  |  | Not Started
30 | Story | 28 | Phase 1 Discover | Identify impacted teams, customers and business processes |  | Each impacted group has a named contact for the communication plan. |  |  | Not Started
31 | Story | 28 | Phase 1 Discover | Identify upstream and downstream dependencies |  | Dependencies logged in the RAID log with owners. |  |  | Not Started
32 | Feature | 22 | Phase 1 Discover | Stakeholder and pain point discovery | Understanding current pain points lets us show value early and build support. | Stakeholder analysis, interview findings and problem statements published. |  |  | Not Started
33 | Story | 32 | Phase 1 Discover | Complete stakeholder roster and power/interest analysis |  | Roster complete; engagement approach defined per quadrant. |  |  | Not Started
34 | Story | 32 | Phase 1 Discover | Conduct empathy interviews with key stakeholder groups |  | Interviews completed across affected groups; themes synthesized. |  |  | Not Started
35 | Story | 32 | Phase 1 Discover | Write problem statements and A3s for top pain points |  | Top pain points documented in the SIG problem statement format. |  |  | Not Started
36 | Feature | 22 | Phase 1 Discover | Requirements and constraints confirmed | Knowing regulatory, security and legal constraints up front avoids late blockers. | Constraints and non-functional requirements approved by Security, Compliance and Legal. |  |  | Not Started
37 | Story | 36 | Phase 1 Discover | Identify regulatory, compliance and policy requirements |  | Requirements listed with an owner. |  |  | Not Started
38 | Story | 36 | Phase 1 Discover | Document security, privacy and records retention needs |  | Needs confirmed with Security and Records or Legal. |  |  | Not Started
39 | Story | 36 | Phase 1 Discover | Complete security and legal preliminary review |  | Findings logged in the RAID log with owners. |  |  | Not Started
40 | Epic |  | Phase 2 Decide | Solution and Approach Decisions | If the solution, delivery approach and cost guardrails are decided and communicated once, then teams can plan releases without reopening debates. |  |  |  | Not Started
41 | Feature | 40 | Phase 2 Decide | Solution option selected and approved | A formal, approved recommendation gives the program a single direction. | Executive sponsor approval recorded for the selected solution option. |  |  | Not Started
42 | Story | 41 | Phase 2 Decide | Name accountable lead for solution selection |  | Lead named in RACI. |  |  | Not Started
43 | Story | 41 | Phase 2 Decide | Agree evaluation criteria for solution options |  | Criteria approved by sponsor and product owner. |  |  | Not Started
44 | Story | 41 | Phase 2 Decide | Facilitate solution option review |  | Options compared against criteria; recommendation drafted. |  |  | Not Started
45 | Story | 41 | Phase 2 Decide | Complete security, legal and financial reviews |  | Sign-offs recorded from each reviewer. |  |  | Not Started
46 | Story | 41 | Phase 2 Decide | Present recommendation for sponsor approval |  | Decision and any conditions recorded in the decision log. |  |  | Not Started
47 | Feature | 40 | Phase 2 Decide | Delivery approach defined | Choosing how we deliver balances speed, risk and long-term value. | Release strategy, MVP and phasing approved by Program Leadership. |  |  | Not Started
48 | Story | 47 | Phase 2 Decide | Define the Minimum Viable Product (MVP) |  | MVP scope and success measures approved. |  |  | Not Started
49 | Story | 47 | Phase 2 Decide | Agree release strategy and phasing |  | Approach recorded with rationale. |  |  | Not Started
50 | Story | 47 | Phase 2 Decide | Confirm build, buy or partner decisions |  | Decisions recorded in the decision log. |  |  | Not Started
51 | Feature | 40 | Phase 2 Decide | Cost guardrails in place | Guardrails prevent cost surprises that erode the business case. | Budget guardrails and cost review cadence approved by Finance. |  |  | Not Started
52 | Story | 51 | Phase 2 Decide | Define budget guardrails |  | Guardrails approved and linked to the business case. |  |  | Not Started
53 | Story | 51 | Phase 2 Decide | Agree cost tracking and chargeback approach |  | Approach published. |  |  | Not Started
54 | Story | 51 | Phase 2 Decide | Set monthly cost review cadence |  | Recurring review scheduled with Finance. |  |  | Not Started
55 | Epic |  | Phase 3 Ready | Delivery Readiness (Enabler) | If teams, partners, environments and tools are ready before the first release, then delivery is not blocked by setup gaps. |  |  |  | Not Started
56 | Feature | 55 | Phase 3 Ready | Teams formed and capacity secured | Dedicated, well-formed teams deliver faster than borrowed capacity. | Teams named with roles filled and capacity confirmed for the first PI. |  |  | Not Started
57 | Story | 56 | Phase 3 Ready | Confirm team structure and roles |  | Roles filled or open roles have a hiring or sourcing plan. |  |  | Not Started
58 | Story | 56 | Phase 3 Ready | Secure capacity commitments from resource managers |  | Commitments recorded for the first PI. |  |  | Not Started
59 | Story | 56 | Phase 3 Ready | Run team launch and working agreements |  | Each team has published working agreements. |  |  | Not Started
60 | Feature | 55 | Phase 3 Ready | Vendors and partners onboarded | Clear contracts and onboarding avoid a slow start. | Contracts signed and partner resources onboarded with access. |  |  | Not Started
61 | Story | 60 | Phase 3 Ready | Finalize statements of work and contracts |  | Contracts signed by Procurement. |  |  | Not Started
62 | Story | 60 | Phase 3 Ready | Onboard partner resources |  | Partner resources have access and have completed orientation. |  |  | Not Started
63 | Feature | 55 | Phase 3 Ready | Environments, tools and access ready | Ready environments remove a common early blocker. | Environments, tools and access confirmed ready by their owners. |  |  | Not Started
64 | Story | 63 | Phase 3 Ready | Confirm environments and tooling available |  | Owners confirm readiness against checklist. |  |  | Not Started
65 | Story | 63 | Phase 3 Ready | Approve access and permissions model |  | Security approves access model. |  |  | Not Started
66 | Epic |  | Phase 4 Deliver | Release Planning and Incremental Delivery | If we deliver in prioritized releases with clear entry and exit criteria, then we deliver value early and reduce go-live risk. |  |  |  | Not Started
67 | Feature | 66 | Phase 4 Deliver | Release roadmap approved | A WSJF-prioritized roadmap sequences the highest value, lowest risk work first. | Roadmap approved by steering committee and aligned to PIs. |  |  | Not Started
68 | Story | 67 | Phase 4 Deliver | Define release entry and exit criteria |  | Criteria approved by product owners and delivery leads. |  |  | Not Started
69 | Story | 67 | Phase 4 Deliver | Facilitate WSJF workshop to prioritize Features and releases |  | Features scored and sequenced. |  |  | Not Started
70 | Story | 67 | Phase 4 Deliver | Publish release roadmap aligned to PIs |  | Roadmap shared with all stakeholders. |  |  | Not Started
71 | Feature | 66 | Phase 4 Deliver | Release 1 (MVP) delivered | An early MVP proves the approach and calibrates estimates for later releases. | Release 1 meets exit criteria and is in use by its intended customers. |  |  | Not Started
72 | Story | 71 | Phase 4 Deliver | Release 1: coordinate delivery across teams and partners |  | Dependencies tracked and resolved through the ART Sync. |  |  | Not Started
73 | Story | 71 | Phase 4 Deliver | Release 1: complete readiness review |  | Readiness checklist signed off by delivery and operations leads. |  |  | Not Started
74 | Story | 71 | Phase 4 Deliver | Release 1: deploy and confirm adoption |  | Release live; adoption measures captured. |  |  | Not Started
75 | Story | 71 | Phase 4 Deliver | Release 1: retrospective and estimate recalibration |  | Lessons applied to the roadmap. |  |  | Not Started
76 | Feature | 66 | Phase 4 Deliver | Release N delivered (copy per release) | Repeatable releases increase throughput as the team learns. | Release meets exit criteria and is in use by its intended customers. |  |  | Not Started
77 | Story | 76 | Phase 4 Deliver | Release N: coordinate delivery across teams and partners |  | Dependencies tracked and resolved through the ART Sync. |  |  | Not Started
78 | Story | 76 | Phase 4 Deliver | Release N: complete readiness review |  | Readiness checklist signed off by delivery and operations leads. |  |  | Not Started
79 | Story | 76 | Phase 4 Deliver | Release N: deploy and confirm adoption |  | Release live; adoption measures captured. |  |  | Not Started
80 | Epic |  | Phase 5 Accept and Go Live | Validation, Acceptance and Go-Live | If every release is tested and accepted by the business before go-live, then trust in the outcome is preserved. |  |  |  | Not Started
81 | Feature | 80 | Phase 5 Accept and Go Live | Acceptance and UAT sign-off | Objective acceptance criteria build business confidence. | Each release has test results and business UAT sign-off. |  |  | Not Started
82 | Story | 81 | Phase 5 Accept and Go Live | Define acceptance criteria and quality thresholds |  | Criteria agreed with business owners. |  |  | Not Started
83 | Story | 81 | Phase 5 Accept and Go Live | Run testing and publish results |  | Results reported against thresholds. |  |  | Not Started
84 | Story | 81 | Phase 5 Accept and Go Live | Obtain business UAT sign-off per release |  | Sign-off recorded from each business owner. |  |  | Not Started
85 | Feature | 80 | Phase 5 Accept and Go Live | Go-live readiness | A rehearsed go-live with a rollback plan reduces business disruption. | Go-live plan and rollback plan approved; Go/No-Go held and recorded. |  |  | Not Started
86 | Story | 85 | Phase 5 Accept and Go Live | Coordinate go-live plan review and approval |  | Plan approved by delivery lead and operations. |  |  | Not Started
87 | Story | 85 | Phase 5 Accept and Go Live | Confirm rollback or contingency plan |  | Plan approved and tested where feasible. |  |  | Not Started
88 | Story | 85 | Phase 5 Accept and Go Live | Hold Go/No-Go decision meeting |  | Decision recorded in decision log. |  |  | Not Started
89 | Epic |  | Cross-cutting | Organizational Change and Communications | If leaders, users and teams hear the right message at the right time, then adoption is faster and resistance is lower. |  |  |  | Not Started
90 | Feature | 89 | Cross-cutting | Communication plan executed | Targeted communication reduces surprises and support load. | Communication plan approved and executed on schedule. |  |  | Not Started
91 | Story | 90 | Cross-cutting | Complete audience analysis |  | Audiences defined with their needs and preferred channels. |  |  | Not Started
92 | Story | 90 | Cross-cutting | Publish leadership update cadence |  | Updates issued on agreed cadence. |  |  | Not Started
93 | Story | 90 | Cross-cutting | Publish user communications ahead of each release |  | Notices sent ahead of each go-live. |  |  | Not Started
94 | Feature | 89 | Cross-cutting | Training and organizational readiness | Prepared people adopt new ways of working faster. | Skills gaps addressed and role changes communicated before go-live. |  |  | Not Started
95 | Story | 94 | Cross-cutting | Complete skills gap assessment |  | Gaps documented per role. |  |  | Not Started
96 | Story | 94 | Cross-cutting | Publish training and readiness plan |  | Plan approved with dates and owners. |  |  | Not Started
97 | Story | 94 | Cross-cutting | Communicate role and support model changes |  | Changes communicated and acknowledged by affected teams. |  |  | Not Started
98 | Epic |  | Phase 6 Close and Sustain | Transition, Closeout and Benefits Realization | If we retire what the program replaces and measure results against the business case, then the organization captures the value it invested for. |  |  |  | Not Started
99 | Feature | 98 | Phase 6 Close and Sustain | Transition to operations complete | A clean handoff and retirement of old ways stop duplicate costs. | Operations has accepted ownership; replaced processes, systems and contracts are retired. |  |  | Not Started
100 | Story | 99 | Phase 6 Close and Sustain | Hand off support and ownership to operations |  | Operations signs off on the support model. |  |  | Not Started
101 | Story | 99 | Phase 6 Close and Sustain | Retire replaced processes, systems or tools |  | Retirement confirmed by owners. |  |  | Not Started
102 | Story | 99 | Phase 6 Close and Sustain | Terminate or adjust related contracts |  | Changes confirmed by Procurement. |  |  | Not Started
103 | Feature | 98 | Phase 6 Close and Sustain | Benefits realized and program closed | Measuring results proves value and informs future investments. | Benefits report compares actuals to the business case; program closed by steering committee. |  |  | Not Started
104 | Story | 103 | Phase 6 Close and Sustain | Measure actual costs and benefits against business case |  | Report reviewed with Finance. |  |  | Not Started
105 | Story | 103 | Phase 6 Close and Sustain | Facilitate final Inspect and Adapt and lessons learned |  | Lessons documented and shared. |  |  | Not Started
106 | Story | 103 | Phase 6 Close and Sustain | Close program and archive artifacts |  | Steering committee approves closure. |  |  | Not Started

## Jira Import
Issue ID | Parent ID | Issue Type | Summary | Description | Labels | Epic Name
1 |  | Epic | Program Mobilization and Strategic Alignment | Epic hypothesis: If we secure a clear executive imperative, governance and an approved business case before delivery begins, then the program will make faster decisions and avoid rework caused by shifting priorities. | Program Phase-0-Mobilize | Program Mobilization and Strategic Alignment
2 | 1 | Feature | Executive imperative and Strategic Themes defined | Benefit hypothesis: A written imperative and Strategic Themes give every team the same answer to 'why are we doing this'. Acceptance criteria: Strategic Themes and OKRs approved by the executive sponsor and published to the program team. | Program Phase-0-Mobilize
3 | 2 | Story | Confirm executive sponsor and named decision-maker(s) | Acceptance criteria: Sponsor and decision-makers are named in the governance charter and have accepted the role. | Program Phase-0-Mobilize
4 | 2 | Story | Facilitate Strategic Themes workshop for the program | Acceptance criteria: Workshop held with business, technology and operations leaders; 2 to 4 themes drafted. | Program Phase-0-Mobilize
5 | 2 | Story | Draft program OKRs aligned to Strategic Themes | Acceptance criteria: Each theme has at least one Objective with measurable Key Results and an owner. | Program Phase-0-Mobilize
6 | 2 | Story | Identify hard date constraints (contract renewals, regulatory or fiscal deadlines) | Acceptance criteria: Constraint dates confirmed with their owners and logged as milestones and dependencies in the RAID log. | Program Phase-0-Mobilize
7 | 1 | Feature | Program governance established | Benefit hypothesis: Defined decision rights and cadence reduce decision latency and escalations. Acceptance criteria: Governance charter and RACI signed off; steering committee calendar issued; RAID log live. | Program Phase-0-Mobilize
8 | 7 | Story | Draft governance charter | Acceptance criteria: Charter covers purpose, scope, decision rights, escalation path and meeting cadence. | Program Phase-0-Mobilize
9 | 7 | Story | Build and validate program RACI | Acceptance criteria: RACI reviewed with each accountable leader; exactly one Accountable per activity. | Program Phase-0-Mobilize
10 | 7 | Story | Schedule steering committee and SAFe Events cadence | Acceptance criteria: Recurring invitations sent for steering committee, PI Planning, System Demos and Inspect and Adapt. | Program Phase-0-Mobilize
11 | 7 | Story | Stand up RAID log and review cadence | Acceptance criteria: RAID log published; owners assigned; weekly review scheduled. | Program Phase-0-Mobilize
12 | 1 | Feature | Program business case approved | Benefit hypothesis: A defensible business case secures funding and sets the benefits we will measure at closeout. Acceptance criteria: Business case reviewed by Finance and the Portfolio; Go decision recorded in the Portfolio Kanban. | Program Phase-0-Mobilize
13 | 12 | Story | Collect current-state cost baseline | Acceptance criteria: Current costs documented by line with Finance or the cost owner as the source. | Program Phase-0-Mobilize
14 | 12 | Story | Collect future-state and one-time cost estimates | Acceptance criteria: Estimates documented with assumptions and source for each line. | Program Phase-0-Mobilize
15 | 12 | Story | Complete Business Case and TCO template | Acceptance criteria: All input cells completed; summary reviewed by Finance. | Program Phase-0-Mobilize
16 | 12 | Story | Present Epic to Lean Portfolio Management for Go/No-Go | Acceptance criteria: Decision and conditions recorded on the Epic. | Program Phase-0-Mobilize
17 | 1 | Feature | Program backlog and tooling ready | Benefit hypothesis: A ready backlog and shared tooling let teams start delivering in the first PI. Acceptance criteria: Jira project configured, accelerator imported, Definition of Ready and Done published. | Program Phase-0-Mobilize
18 | 17 | Story | Configure Jira project, issue hierarchy and workflows | Acceptance criteria: Epic, Feature and Story types available; workflow statuses agreed. | Program Phase-0-Mobilize
19 | 17 | Story | Import and tailor the Program Jira Accelerator | Acceptance criteria: Items imported; out-of-scope items closed with a reason; owners assigned. | Program Phase-0-Mobilize
20 | 17 | Story | Publish Definition of Ready and Definition of Done | Acceptance criteria: DoR and DoD reviewed with team leads and posted in the team space. | Program Phase-0-Mobilize
21 | 17 | Story | Build program status dashboard | Acceptance criteria: Dashboard shows Feature progress, milestones and top risks; shared with steering committee. | Program Phase-0-Mobilize
22 |  | Epic | Discovery and Current State Assessment | Epic hypothesis: If we understand the current state, who is affected and what they need, then we will scope the right work and avoid surprises at go-live. | Program Phase-1-Discover | Discovery and Current State Assessment
23 | 22 | Feature | Current state baseline documented | Benefit hypothesis: A clear baseline lets us measure improvement and spot what can be retired. Acceptance criteria: Current processes, systems, costs and performance measures documented and validated by their owners. | Program Phase-1-Discover
24 | 23 | Story | Document current processes and workflows in scope | Acceptance criteria: Process maps reviewed with process owners. | Program Phase-1-Discover
25 | 23 | Story | Inventory systems, tools and assets in scope | Acceptance criteria: Inventory lists owner, usage and criticality for each item. | Program Phase-1-Discover
26 | 23 | Story | Capture baseline performance measures | Acceptance criteria: Baseline values recorded with source and date for each measure to be tracked. | Program Phase-1-Discover
27 | 23 | Story | Agree what will be kept, changed or retired | Acceptance criteria: Disposition reviewed and accepted by owners. | Program Phase-1-Discover
28 | 22 | Feature | Stakeholder and impact map | Benefit hypothesis: Mapping everyone affected early prevents missed stakeholders and broken handoffs. Acceptance criteria: Impact map published showing suppliers, inputs, process, outputs and customers, with impacted teams named. | Program Phase-1-Discover
29 | 28 | Story | Facilitate SIPOC workshop for the program scope | Acceptance criteria: SIPOC completed and validated with supplier and customer representatives. | Program Phase-1-Discover
30 | 28 | Story | Identify impacted teams, customers and business processes | Acceptance criteria: Each impacted group has a named contact for the communication plan. | Program Phase-1-Discover
31 | 28 | Story | Identify upstream and downstream dependencies | Acceptance criteria: Dependencies logged in the RAID log with owners. | Program Phase-1-Discover
32 | 22 | Feature | Stakeholder and pain point discovery | Benefit hypothesis: Understanding current pain points lets us show value early and build support. Acceptance criteria: Stakeholder analysis, interview findings and problem statements published. | Program Phase-1-Discover
33 | 32 | Story | Complete stakeholder roster and power/interest analysis | Acceptance criteria: Roster complete; engagement approach defined per quadrant. | Program Phase-1-Discover
34 | 32 | Story | Conduct empathy interviews with key stakeholder groups | Acceptance criteria: Interviews completed across affected groups; themes synthesized. | Program Phase-1-Discover
35 | 32 | Story | Write problem statements and A3s for top pain points | Acceptance criteria: Top pain points documented in the SIG problem statement format. | Program Phase-1-Discover
36 | 22 | Feature | Requirements and constraints confirmed | Benefit hypothesis: Knowing regulatory, security and legal constraints up front avoids late blockers. Acceptance criteria: Constraints and non-functional requirements approved by Security, Compliance and Legal. | Program Phase-1-Discover
37 | 36 | Story | Identify regulatory, compliance and policy requirements | Acceptance criteria: Requirements listed with an owner. | Program Phase-1-Discover
38 | 36 | Story | Document security, privacy and records retention needs | Acceptance criteria: Needs confirmed with Security and Records or Legal. | Program Phase-1-Discover
39 | 36 | Story | Complete security and legal preliminary review | Acceptance criteria: Findings logged in the RAID log with owners. | Program Phase-1-Discover
40 |  | Epic | Solution and Approach Decisions | Epic hypothesis: If the solution, delivery approach and cost guardrails are decided and communicated once, then teams can plan releases without reopening debates. | Program Phase-2-Decide | Solution and Approach Decisions
41 | 40 | Feature | Solution option selected and approved | Benefit hypothesis: A formal, approved recommendation gives the program a single direction. Acceptance criteria: Executive sponsor approval recorded for the selected solution option. | Program Phase-2-Decide
42 | 41 | Story | Name accountable lead for solution selection | Acceptance criteria: Lead named in RACI. | Program Phase-2-Decide
43 | 41 | Story | Agree evaluation criteria for solution options | Acceptance criteria: Criteria approved by sponsor and product owner. | Program Phase-2-Decide
44 | 41 | Story | Facilitate solution option review | Acceptance criteria: Options compared against criteria; recommendation drafted. | Program Phase-2-Decide
45 | 41 | Story | Complete security, legal and financial reviews | Acceptance criteria: Sign-offs recorded from each reviewer. | Program Phase-2-Decide
46 | 41 | Story | Present recommendation for sponsor approval | Acceptance criteria: Decision and any conditions recorded in the decision log. | Program Phase-2-Decide
47 | 40 | Feature | Delivery approach defined | Benefit hypothesis: Choosing how we deliver balances speed, risk and long-term value. Acceptance criteria: Release strategy, MVP and phasing approved by Program Leadership. | Program Phase-2-Decide
48 | 47 | Story | Define the Minimum Viable Product (MVP) | Acceptance criteria: MVP scope and success measures approved. | Program Phase-2-Decide
49 | 47 | Story | Agree release strategy and phasing | Acceptance criteria: Approach recorded with rationale. | Program Phase-2-Decide
50 | 47 | Story | Confirm build, buy or partner decisions | Acceptance criteria: Decisions recorded in the decision log. | Program Phase-2-Decide
51 | 40 | Feature | Cost guardrails in place | Benefit hypothesis: Guardrails prevent cost surprises that erode the business case. Acceptance criteria: Budget guardrails and cost review cadence approved by Finance. | Program Phase-2-Decide
52 | 51 | Story | Define budget guardrails | Acceptance criteria: Guardrails approved and linked to the business case. | Program Phase-2-Decide
53 | 51 | Story | Agree cost tracking and chargeback approach | Acceptance criteria: Approach published. | Program Phase-2-Decide
54 | 51 | Story | Set monthly cost review cadence | Acceptance criteria: Recurring review scheduled with Finance. | Program Phase-2-Decide
55 |  | Epic | Delivery Readiness (Enabler) | Epic hypothesis: If teams, partners, environments and tools are ready before the first release, then delivery is not blocked by setup gaps. | Program Phase-3-Ready | Delivery Readiness (Enabler)
56 | 55 | Feature | Teams formed and capacity secured | Benefit hypothesis: Dedicated, well-formed teams deliver faster than borrowed capacity. Acceptance criteria: Teams named with roles filled and capacity confirmed for the first PI. | Program Phase-3-Ready
57 | 56 | Story | Confirm team structure and roles | Acceptance criteria: Roles filled or open roles have a hiring or sourcing plan. | Program Phase-3-Ready
58 | 56 | Story | Secure capacity commitments from resource managers | Acceptance criteria: Commitments recorded for the first PI. | Program Phase-3-Ready
59 | 56 | Story | Run team launch and working agreements | Acceptance criteria: Each team has published working agreements. | Program Phase-3-Ready
60 | 55 | Feature | Vendors and partners onboarded | Benefit hypothesis: Clear contracts and onboarding avoid a slow start. Acceptance criteria: Contracts signed and partner resources onboarded with access. | Program Phase-3-Ready
61 | 60 | Story | Finalize statements of work and contracts | Acceptance criteria: Contracts signed by Procurement. | Program Phase-3-Ready
62 | 60 | Story | Onboard partner resources | Acceptance criteria: Partner resources have access and have completed orientation. | Program Phase-3-Ready
63 | 55 | Feature | Environments, tools and access ready | Benefit hypothesis: Ready environments remove a common early blocker. Acceptance criteria: Environments, tools and access confirmed ready by their owners. | Program Phase-3-Ready
64 | 63 | Story | Confirm environments and tooling available | Acceptance criteria: Owners confirm readiness against checklist. | Program Phase-3-Ready
65 | 63 | Story | Approve access and permissions model | Acceptance criteria: Security approves access model. | Program Phase-3-Ready
66 |  | Epic | Release Planning and Incremental Delivery | Epic hypothesis: If we deliver in prioritized releases with clear entry and exit criteria, then we deliver value early and reduce go-live risk. | Program Phase-4-Deliver | Release Planning and Incremental Delivery
67 | 66 | Feature | Release roadmap approved | Benefit hypothesis: A WSJF-prioritized roadmap sequences the highest value, lowest risk work first. Acceptance criteria: Roadmap approved by steering committee and aligned to PIs. | Program Phase-4-Deliver
68 | 67 | Story | Define release entry and exit criteria | Acceptance criteria: Criteria approved by product owners and delivery leads. | Program Phase-4-Deliver
69 | 67 | Story | Facilitate WSJF workshop to prioritize Features and releases | Acceptance criteria: Features scored and sequenced. | Program Phase-4-Deliver
70 | 67 | Story | Publish release roadmap aligned to PIs | Acceptance criteria: Roadmap shared with all stakeholders. | Program Phase-4-Deliver
71 | 66 | Feature | Release 1 (MVP) delivered | Benefit hypothesis: An early MVP proves the approach and calibrates estimates for later releases. Acceptance criteria: Release 1 meets exit criteria and is in use by its intended customers. | Program Phase-4-Deliver
72 | 71 | Story | Release 1: coordinate delivery across teams and partners | Acceptance criteria: Dependencies tracked and resolved through the ART Sync. | Program Phase-4-Deliver
73 | 71 | Story | Release 1: complete readiness review | Acceptance criteria: Readiness checklist signed off by delivery and operations leads. | Program Phase-4-Deliver
74 | 71 | Story | Release 1: deploy and confirm adoption | Acceptance criteria: Release live; adoption measures captured. | Program Phase-4-Deliver
75 | 71 | Story | Release 1: retrospective and estimate recalibration | Acceptance criteria: Lessons applied to the roadmap. | Program Phase-4-Deliver
76 | 66 | Feature | Release N delivered (copy per release) | Benefit hypothesis: Repeatable releases increase throughput as the team learns. Acceptance criteria: Release meets exit criteria and is in use by its intended customers. | Program Phase-4-Deliver
77 | 76 | Story | Release N: coordinate delivery across teams and partners | Acceptance criteria: Dependencies tracked and resolved through the ART Sync. | Program Phase-4-Deliver
78 | 76 | Story | Release N: complete readiness review | Acceptance criteria: Readiness checklist signed off by delivery and operations leads. | Program Phase-4-Deliver
79 | 76 | Story | Release N: deploy and confirm adoption | Acceptance criteria: Release live; adoption measures captured. | Program Phase-4-Deliver
80 |  | Epic | Validation, Acceptance and Go-Live | Epic hypothesis: If every release is tested and accepted by the business before go-live, then trust in the outcome is preserved. | Program Phase-5-Accept-and-Go-Live | Validation, Acceptance and Go-Live
81 | 80 | Feature | Acceptance and UAT sign-off | Benefit hypothesis: Objective acceptance criteria build business confidence. Acceptance criteria: Each release has test results and business UAT sign-off. | Program Phase-5-Accept-and-Go-Live
82 | 81 | Story | Define acceptance criteria and quality thresholds | Acceptance criteria: Criteria agreed with business owners. | Program Phase-5-Accept-and-Go-Live
83 | 81 | Story | Run testing and publish results | Acceptance criteria: Results reported against thresholds. | Program Phase-5-Accept-and-Go-Live
84 | 81 | Story | Obtain business UAT sign-off per release | Acceptance criteria: Sign-off recorded from each business owner. | Program Phase-5-Accept-and-Go-Live
85 | 80 | Feature | Go-live readiness | Benefit hypothesis: A rehearsed go-live with a rollback plan reduces business disruption. Acceptance criteria: Go-live plan and rollback plan approved; Go/No-Go held and recorded. | Program Phase-5-Accept-and-Go-Live
86 | 85 | Story | Coordinate go-live plan review and approval | Acceptance criteria: Plan approved by delivery lead and operations. | Program Phase-5-Accept-and-Go-Live
87 | 85 | Story | Confirm rollback or contingency plan | Acceptance criteria: Plan approved and tested where feasible. | Program Phase-5-Accept-and-Go-Live
88 | 85 | Story | Hold Go/No-Go decision meeting | Acceptance criteria: Decision recorded in decision log. | Program Phase-5-Accept-and-Go-Live
89 |  | Epic | Organizational Change and Communications | Epic hypothesis: If leaders, users and teams hear the right message at the right time, then adoption is faster and resistance is lower. | Program Cross-cutting | Organizational Change and Communications
90 | 89 | Feature | Communication plan executed | Benefit hypothesis: Targeted communication reduces surprises and support load. Acceptance criteria: Communication plan approved and executed on schedule. | Program Cross-cutting
91 | 90 | Story | Complete audience analysis | Acceptance criteria: Audiences defined with their needs and preferred channels. | Program Cross-cutting
92 | 90 | Story | Publish leadership update cadence | Acceptance criteria: Updates issued on agreed cadence. | Program Cross-cutting
93 | 90 | Story | Publish user communications ahead of each release | Acceptance criteria: Notices sent ahead of each go-live. | Program Cross-cutting
94 | 89 | Feature | Training and organizational readiness | Benefit hypothesis: Prepared people adopt new ways of working faster. Acceptance criteria: Skills gaps addressed and role changes communicated before go-live. | Program Cross-cutting
95 | 94 | Story | Complete skills gap assessment | Acceptance criteria: Gaps documented per role. | Program Cross-cutting
96 | 94 | Story | Publish training and readiness plan | Acceptance criteria: Plan approved with dates and owners. | Program Cross-cutting
97 | 94 | Story | Communicate role and support model changes | Acceptance criteria: Changes communicated and acknowledged by affected teams. | Program Cross-cutting
98 |  | Epic | Transition, Closeout and Benefits Realization | Epic hypothesis: If we retire what the program replaces and measure results against the business case, then the organization captures the value it invested for. | Program Phase-6-Close-and-Sustain | Transition, Closeout and Benefits Realization
99 | 98 | Feature | Transition to operations complete | Benefit hypothesis: A clean handoff and retirement of old ways stop duplicate costs. Acceptance criteria: Operations has accepted ownership; replaced processes, systems and contracts are retired. | Program Phase-6-Close-and-Sustain
100 | 99 | Story | Hand off support and ownership to operations | Acceptance criteria: Operations signs off on the support model. | Program Phase-6-Close-and-Sustain
101 | 99 | Story | Retire replaced processes, systems or tools | Acceptance criteria: Retirement confirmed by owners. | Program Phase-6-Close-and-Sustain
102 | 99 | Story | Terminate or adjust related contracts | Acceptance criteria: Changes confirmed by Procurement. | Program Phase-6-Close-and-Sustain
103 | 98 | Feature | Benefits realized and program closed | Benefit hypothesis: Measuring results proves value and informs future investments. Acceptance criteria: Benefits report compares actuals to the business case; program closed by steering committee. | Program Phase-6-Close-and-Sustain
104 | 103 | Story | Measure actual costs and benefits against business case | Acceptance criteria: Report reviewed with Finance. | Program Phase-6-Close-and-Sustain
105 | 103 | Story | Facilitate final Inspect and Adapt and lessons learned | Acceptance criteria: Lessons documented and shared. | Program Phase-6-Close-and-Sustain
106 | 103 | Story | Close program and archive artifacts | Acceptance criteria: Steering committee approves closure. | Program Phase-6-Close-and-Sustain