## Start Here
Program Jira Accelerator (Lite)
Program and project management backlog for any large initiative ¦ SIG Template v1.3
Quick start | 1. Tailor the Backlog View only: delete what is out of scope, rename releases and add your own items. The Jira Import tab updates itself. 2. Delete any blank rows at the bottom of Jira Import, then save that tab as CSV (File > Save As > CSV UTF-8). 3. In Jira, open the CSV importer (System > External System Import > CSV), map Issue ID, Parent ID, Issue Type, Summary, Description, Labels and Epic Name, then import.
Contents | 8 Epics, 23 Features (no Stories, so your teams can write their own).
Good to know | No Feature issue type in your Jira? Map Features to Epic and Epics to a higher type such as Initiative, or import Features as Epics and add the Epic name as a label. The ‘Release N delivered’ Feature is a template: copy it once per release. If you add rows to the Backlog View, drag the Jira Import table’s bottom-right corner down to match; the new rows fill in on their own.
© 2026 Stephens Insight Group LLC. Capital In. Value Out. ¦ stephensinsightgroup.com

## Backlog View
ID | Level | Parent ID | Phase | Summary | Hypothesis | Acceptance Criteria | Owner | Target PI | Status
1 | Epic |  | Phase 0 Mobilize | Program Mobilization and Strategic Alignment | If we secure a clear executive imperative, governance and an approved business case before delivery begins, then the program will make faster decisions and avoid rework caused by shifting priorities. |  |  |  | Not started
2 | Feature | 1 | Phase 0 Mobilize | Executive imperative and Strategic Themes defined | A written imperative and Strategic Themes give every team the same answer to 'why are we doing this'. | Strategic Themes and OKRs approved by the executive sponsor and published to the program team. |  |  | Not started
3 | Feature | 1 | Phase 0 Mobilize | Program governance established | Defined decision rights and cadence reduce decision latency and escalations. | Governance charter and RACI signed off; steering committee calendar issued; RAID log live. |  |  | Not started
4 | Feature | 1 | Phase 0 Mobilize | Program business case approved | A defensible business case secures funding and sets the benefits we will measure at closeout. | Business case reviewed by Finance and the Portfolio; Go decision recorded in the Portfolio Kanban. |  |  | Not started
5 | Feature | 1 | Phase 0 Mobilize | Program backlog and tooling ready | A ready backlog and shared tooling let teams start delivering in the first PI. | Jira project configured, accelerator imported, Definition of Ready and Done published. |  |  | Not started
6 | Epic |  | Phase 1 Discover | Discovery and Current State Assessment | If we understand the current state, who is affected and what they need, then we will scope the right work and avoid surprises at go-live. |  |  |  | Not started
7 | Feature | 6 | Phase 1 Discover | Current state baseline documented | A clear baseline lets us measure improvement and spot what can be retired. | Current processes, systems, costs and performance measures documented and validated by their owners. |  |  | Not started
8 | Feature | 6 | Phase 1 Discover | Stakeholder and impact map | Mapping everyone affected early prevents missed stakeholders and broken handoffs. | Impact map published showing suppliers, inputs, process, outputs and customers, with impacted teams named. |  |  | Not started
9 | Feature | 6 | Phase 1 Discover | Stakeholder and pain point discovery | Understanding current pain points lets us show value early and build support. | Stakeholder analysis, interview findings and problem statements published. |  |  | Not started
10 | Feature | 6 | Phase 1 Discover | Requirements and constraints confirmed | Knowing regulatory, security and legal constraints up front avoids late blockers. | Constraints and non-functional requirements approved by Security, Compliance and Legal. |  |  | Not started
11 | Epic |  | Phase 2 Decide | Solution and Approach Decisions | If the solution, delivery approach and cost guardrails are decided and communicated once, then teams can plan releases without reopening debates. |  |  |  | Not started
12 | Feature | 11 | Phase 2 Decide | Solution option selected and approved | A formal, approved recommendation gives the program a single direction. | Executive sponsor approval recorded for the selected solution option. |  |  | Not started
13 | Feature | 11 | Phase 2 Decide | Delivery approach defined | Choosing how we deliver balances speed, risk and long-term value. | Release strategy, MVP and phasing approved by Program Leadership. |  |  | Not started
14 | Feature | 11 | Phase 2 Decide | Cost guardrails in place | Guardrails prevent cost surprises that erode the business case. | Budget guardrails and cost review cadence approved by Finance. |  |  | Not started
15 | Epic |  | Phase 3 Ready | Delivery Readiness (Enabler) | If teams, partners, environments and tools are ready before the first release, then delivery is not blocked by setup gaps. |  |  |  | Not started
16 | Feature | 15 | Phase 3 Ready | Teams formed and capacity secured | Dedicated, well-formed teams deliver faster than borrowed capacity. | Teams named with roles filled and capacity confirmed for the first PI. |  |  | Not started
17 | Feature | 15 | Phase 3 Ready | Vendors and partners onboarded | Clear contracts and onboarding avoid a slow start. | Contracts signed and partner resources onboarded with access. |  |  | Not started
18 | Feature | 15 | Phase 3 Ready | Environments, tools and access ready | Ready environments remove a common early blocker. | Environments, tools and access confirmed ready by their owners. |  |  | Not started
19 | Epic |  | Phase 4 Deliver | Release Planning and Incremental Delivery | If we deliver in prioritized releases with clear entry and exit criteria, then we deliver value early and reduce go-live risk. |  |  |  | Not started
20 | Feature | 19 | Phase 4 Deliver | Release roadmap approved | A WSJF-prioritized roadmap sequences the highest value, lowest risk work first. | Roadmap approved by steering committee and aligned to PIs. |  |  | Not started
21 | Feature | 19 | Phase 4 Deliver | Release 1 (MVP) delivered | An early MVP proves the approach and calibrates estimates for later releases. | Release 1 meets exit criteria and is in use by its intended customers. |  |  | Not started
22 | Feature | 19 | Phase 4 Deliver | Release N delivered (copy per release) | Repeatable releases increase throughput as the team learns. | Release meets exit criteria and is in use by its intended customers. |  |  | Not started
23 | Epic |  | Phase 5 Accept and Go Live | Validation, Acceptance and Go-Live | If every release is tested and accepted by the business before go-live, then trust in the outcome is preserved. |  |  |  | Not started
24 | Feature | 23 | Phase 5 Accept and Go Live | Acceptance and UAT sign-off | Objective acceptance criteria build business confidence. | Each release has test results and business UAT sign-off. |  |  | Not started
25 | Feature | 23 | Phase 5 Accept and Go Live | Go-live readiness | A rehearsed go-live with a rollback plan reduces business disruption. | Go-live plan and rollback plan approved; Go/No-Go held and recorded. |  |  | Not started
26 | Epic |  | Cross-cutting | Organizational Change and Communications | If leaders, users and teams hear the right message at the right time, then adoption is faster and resistance is lower. |  |  |  | Not started
27 | Feature | 26 | Cross-cutting | Communication plan executed | Targeted communication reduces surprises and support load. | Communication plan approved and executed on schedule. |  |  | Not started
28 | Feature | 26 | Cross-cutting | Training and organizational readiness | Prepared people adopt new ways of working faster. | Skills gaps addressed and role changes communicated before go-live. |  |  | Not started
29 | Epic |  | Phase 6 Close and Sustain | Transition, Closeout and Benefits Realization | If we retire what the program replaces and measure results against the business case, then the organization captures the value it invested for. |  |  |  | Not started
30 | Feature | 29 | Phase 6 Close and Sustain | Transition to operations complete | A clean handoff and retirement of old ways stop duplicate costs. | Operations has accepted ownership; replaced processes, systems and contracts are retired. |  |  | Not started
31 | Feature | 29 | Phase 6 Close and Sustain | Benefits realized and program closed | Measuring results proves value and informs future investments. | Benefits report compares actuals to the business case; program closed by steering committee. |  |  | Not started

## Jira Import
Issue ID | Parent ID | Issue Type | Summary | Description | Labels | Epic Name