## Start Here
Program Jira Accelerator
Program and project management backlog for any large initiative ¦ SIG Template v1.3
Quick start | 1. Tailor the Backlog View only: delete what is out of scope, rename releases and add your own items. The Jira Import tab updates itself. 2. Delete any blank rows at the bottom of Jira Import, then save that tab as CSV (File > Save As > CSV UTF-8). 3. In Jira, open the CSV importer (System > External System Import > CSV), map Issue ID, Parent ID, Issue Type, Summary, Description, Labels and Epic Name, then import.
Contents | 8 Epics, 23 Features, 75 Stories.
Good to know | No Feature issue type in your Jira? Map Features to Epic and Epics to a higher type such as Initiative, or import Features as Epics and add the Epic name as a label. The ‘Release N delivered’ Feature is a template: copy it once per release. If you add rows to the Backlog View, drag the Jira Import table’s bottom-right corner down to match; the new rows fill in on their own.
© 2026 Stephens Insight Group LLC. Capital In. Value Out. ¦ stephensinsightgroup.com

## Backlog View
ID | Level | Parent ID | Phase | Summary | Hypothesis | Acceptance Criteria | Owner | Target PI | Status
1 | Epic |  | Phase 0 Mobilize | Program Mobilization and Strategic Alignment | If we secure a clear executive imperative, governance and an approved business case before delivery begins, then the program will make faster decisions and avoid rework caused by shifting priorities. |  |  |  | Not started
2 | Feature | 1 | Phase 0 Mobilize | Executive imperative and Strategic Themes defined | A written imperative and Strategic Themes give every team the same answer to 'why are we doing this'. | Strategic Themes and OKRs approved by the executive sponsor and published to the program team. |  |  | Not started
3 | Story | 2 | Phase 0 Mobilize | Confirm executive sponsor and named decision-maker(s) |  | Sponsor and decision-makers are named in the governance charter and have accepted the role. |  |  | Not started
4 | Story | 2 | Phase 0 Mobilize | Facilitate Strategic Themes workshop for the program |  | Workshop held with business, technology and operations leaders; 2 to 4 themes drafted. |  |  | Not started
5 | Story | 2 | Phase 0 Mobilize | Draft program OKRs aligned to Strategic Themes |  | Each theme has at least one Objective with measurable Key Results and an owner. |  |  | Not started
6 | Story | 2 | Phase 0 Mobilize | Identify hard date constraints (contract renewals, regulatory or fiscal deadlines) |  | Constraint dates confirmed with their owners and logged as milestones and dependencies in the RAID log. |  |  | Not started
7 | Feature | 1 | Phase 0 Mobilize | Program governance established | Defined decision rights and cadence reduce decision latency and escalations. | Governance charter and RACI signed off; steering committee calendar issued; RAID log live. |  |  | Not started
8 | Story | 7 | Phase 0 Mobilize | Draft governance charter |  | Charter covers purpose, scope, decision rights, escalation path and meeting cadence. |  |  | Not started
9 | Story | 7 | Phase 0 Mobilize | Build and validate program RACI |  | RACI reviewed with each accountable leader; exactly one Accountable per activity. |  |  | Not started
10 | Story | 7 | Phase 0 Mobilize | Schedule steering committee and SAFe Events cadence |  | Recurring invitations sent for steering committee, PI Planning, System Demos and Inspect and Adapt. |  |  | Not started
11 | Story | 7 | Phase 0 Mobilize | Stand up RAID log and review cadence |  | RAID log published; owners assigned; weekly review scheduled. |  |  | Not started
12 | Feature | 1 | Phase 0 Mobilize | Program business case approved | A defensible business case secures funding and sets the benefits we will measure at closeout. | Business case reviewed by Finance and the Portfolio; Go decision recorded in the Portfolio Kanban. |  |  | Not started
13 | Story | 12 | Phase 0 Mobilize | Collect current-state cost baseline |  | Current costs documented by line with Finance or the cost owner as the source. |  |  | Not started
14 | Story | 12 | Phase 0 Mobilize | Collect future-state and one-time cost estimates |  | Estimates documented with assumptions and source for each line. |  |  | Not started
15 | Story | 12 | Phase 0 Mobilize | Complete Business Case and TCO template |  | All input cells completed; summary reviewed by Finance. |  |  | Not started
16 | Story | 12 | Phase 0 Mobilize | Present Epic to Lean Portfolio Management for Go/No-Go |  | Decision and conditions recorded on the Epic. |  |  | Not started
17 | Feature | 1 | Phase 0 Mobilize | Program backlog and tooling ready | A ready backlog and shared tooling let teams start delivering in the first PI. | Jira project configured, accelerator imported, Definition of Ready and Done published. |  |  | Not started
18 | Story | 17 | Phase 0 Mobilize | Configure Jira project, issue hierarchy and workflows |  | Epic, Feature and Story types available; workflow statuses agreed. |  |  | Not started
19 | Story | 17 | Phase 0 Mobilize | Import and tailor the Program Jira Accelerator |  | Items imported; out-of-scope items closed with a reason; owners assigned. |  |  | Not started
20 | Story | 17 | Phase 0 Mobilize | Publish Definition of Ready and Definition of Done |  | DoR and DoD reviewed with team leads and posted in the team space. |  |  | Not started
21 | Story | 17 | Phase 0 Mobilize | Build program status dashboard |  | Dashboard shows Feature progress, milestones and top risks; shared with steering committee. |  |  | Not started
22 | Epic |  | Phase 1 Discover | Discovery and Current State Assessment | If we understand the current state, who is affected and what they need, then we will scope the right work and avoid surprises at go-live. |  |  |  | Not started
23 | Feature | 22 | Phase 1 Discover | Current state baseline documented | A clear baseline lets us measure improvement and spot what can be retired. | Current processes, systems, costs and performance measures documented and validated by their owners. |  |  | Not started
24 | Story | 23 | Phase 1 Discover | Document current processes and workflows in scope |  | Process maps reviewed with process owners. |  |  | Not started
25 | Story | 23 | Phase 1 Discover | Inventory systems, tools and assets in scope |  | Inventory lists owner, usage and criticality for each item. |  |  | Not started
26 | Story | 23 | Phase 1 Discover | Capture baseline performance measures |  | Baseline values recorded with source and date for each measure to be tracked. |  |  | Not started
27 | Story | 23 | Phase 1 Discover | Agree what will be kept, changed or retired |  | Disposition reviewed and accepted by owners. |  |  | Not started
28 | Feature | 22 | Phase 1 Discover | Stakeholder and impact map | Mapping everyone affected early prevents missed stakeholders and broken handoffs. | Impact map published showing suppliers, inputs, process, outputs and customers, with impacted teams named. |  |  | Not started
29 | Story | 28 | Phase 1 Discover | Facilitate SIPOC workshop for the program scope |  | SIPOC completed and validated with supplier and customer representatives. |  |  | Not started
30 | Story | 28 | Phase 1 Discover | Identify impacted teams, customers and business processes |  | Each impacted group has a named contact for the communication plan. |  |  | Not started
31 | Story | 28 | Phase 1 Discover | Identify upstream and downstream dependencies |  | Dependencies logged in the RAID log with owners. |  |  | Not started
32 | Feature | 22 | Phase 1 Discover | Stakeholder and pain point discovery | Understanding current pain points lets us show value early and build support. | Stakeholder analysis, interview findings and problem statements published. |  |  | Not started
33 | Story | 32 | Phase 1 Discover | Complete stakeholder roster and power/interest analysis |  | Roster complete; engagement approach defined per quadrant. |  |  | Not started
34 | Story | 32 | Phase 1 Discover | Conduct empathy interviews with key stakeholder groups |  | Interviews completed across affected groups; themes synthesized. |  |  | Not started
35 | Story | 32 | Phase 1 Discover | Write problem statements and A3s for top pain points |  | Top pain points documented in the SIG problem statement format. |  |  | Not started
36 | Feature | 22 | Phase 1 Discover | Requirements and constraints confirmed | Knowing regulatory, security and legal constraints up front avoids late blockers. | Constraints and non-functional requirements approved by Security, Compliance and Legal. |  |  | Not started
37 | Story | 36 | Phase 1 Discover | Identify regulatory, compliance and policy requirements |  | Requirements listed with an owner. |  |  | Not started
38 | Story | 36 | Phase 1 Discover | Document security, privacy and records retention needs |  | Needs confirmed with Security and Records or Legal. |  |  | Not started
39 | Story | 36 | Phase 1 Discover | Complete security and legal preliminary review |  | Findings logged in the RAID log with owners. |  |  | Not started
40 | Epic |  | Phase 2 Decide | Solution and Approach Decisions | If the solution, delivery approach and cost guardrails are decided and communicated once, then teams can plan releases without reopening debates. |  |  |  | Not started
41 | Feature | 40 | Phase 2 Decide | Solution option selected and approved | A formal, approved recommendation gives the program a single direction. | Executive sponsor approval recorded for the selected solution option. |  |  | Not started
42 | Story | 41 | Phase 2 Decide | Name accountable lead for solution selection |  | Lead named in RACI. |  |  | Not started
43 | Story | 41 | Phase 2 Decide | Agree evaluation criteria for solution options |  | Criteria approved by sponsor and product owner. |  |  | Not started
44 | Story | 41 | Phase 2 Decide | Facilitate solution option review |  | Options compared against criteria; recommendation drafted. |  |  | Not started
45 | Story | 41 | Phase 2 Decide | Complete security, legal and financial reviews |  | Sign-offs recorded from each reviewer. |  |  | Not started
46 | Story | 41 | Phase 2 Decide | Present recommendation for sponsor approval |  | Decision and any conditions recorded in the decision log. |  |  | Not started
47 | Feature | 40 | Phase 2 Decide | Delivery approach defined | Choosing how we deliver balances speed, risk and long-term value. | Release strategy, MVP and phasing approved by Program Leadership. |  |  | Not started
48 | Story | 47 | Phase 2 Decide | Define the Minimum Viable Product (MVP) |  | MVP scope and success measures approved. |  |  | Not started
49 | Story | 47 | Phase 2 Decide | Agree release strategy and phasing |  | Approach recorded with rationale. |  |  | Not started
50 | Story | 47 | Phase 2 Decide | Confirm build, buy or partner decisions |  | Decisions recorded in the decision log. |  |  | Not started
51 | Feature | 40 | Phase 2 Decide | Cost guardrails in place | Guardrails prevent cost surprises that erode the business case. | Budget guardrails and cost review cadence approved by Finance. |  |  | Not started
52 | Story | 51 | Phase 2 Decide | Define budget guardrails |  | Guardrails approved and linked to the business case. |  |  | Not started
53 | Story | 51 | Phase 2 Decide | Agree cost tracking and chargeback approach |  | Approach published. |  |  | Not started
54 | Story | 51 | Phase 2 Decide | Set monthly cost review cadence |  | Recurring review scheduled with Finance. |  |  | Not started
55 | Epic |  | Phase 3 Ready | Delivery Readiness (Enabler) | If teams, partners, environments and tools are ready before the first release, then delivery is not blocked by setup gaps. |  |  |  | Not started
56 | Feature | 55 | Phase 3 Ready | Teams formed and capacity secured | Dedicated, well-formed teams deliver faster than borrowed capacity. | Teams named with roles filled and capacity confirmed for the first PI. |  |  | Not started
57 | Story | 56 | Phase 3 Ready | Confirm team structure and roles |  | Roles filled or open roles have a hiring or sourcing plan. |  |  | Not started
58 | Story | 56 | Phase 3 Ready | Secure capacity commitments from resource managers |  | Commitments recorded for the first PI. |  |  | Not started
59 | Story | 56 | Phase 3 Ready | Run team launch and working agreements |  | Each team has published working agreements. |  |  | Not started
60 | Feature | 55 | Phase 3 Ready | Vendors and partners onboarded | Clear contracts and onboarding avoid a slow start. | Contracts signed and partner resources onboarded with access. |  |  | Not started
61 | Story | 60 | Phase 3 Ready | Finalize statements of work and contracts |  | Contracts signed by Procurement. |  |  | Not started
62 | Story | 60 | Phase 3 Ready | Onboard partner resources |  | Partner resources have access and have completed orientation. |  |  | Not started
63 | Feature | 55 | Phase 3 Ready | Environments, tools and access ready | Ready environments remove a common early blocker. | Environments, tools and access confirmed ready by their owners. |  |  | Not started
64 | Story | 63 | Phase 3 Ready | Confirm environments and tooling available |  | Owners confirm readiness against checklist. |  |  | Not started
65 | Story | 63 | Phase 3 Ready | Approve access and permissions model |  | Security approves access model. |  |  | Not started
66 | Epic |  | Phase 4 Deliver | Release Planning and Incremental Delivery | If we deliver in prioritized releases with clear entry and exit criteria, then we deliver value early and reduce go-live risk. |  |  |  | Not started
67 | Feature | 66 | Phase 4 Deliver | Release roadmap approved | A WSJF-prioritized roadmap sequences the highest value, lowest risk work first. | Roadmap approved by steering committee and aligned to PIs. |  |  | Not started
68 | Story | 67 | Phase 4 Deliver | Define release entry and exit criteria |  | Criteria approved by product owners and delivery leads. |  |  | Not started
69 | Story | 67 | Phase 4 Deliver | Facilitate WSJF workshop to prioritize Features and releases |  | Features scored and sequenced. |  |  | Not started
70 | Story | 67 | Phase 4 Deliver | Publish release roadmap aligned to PIs |  | Roadmap shared with all stakeholders. |  |  | Not started
71 | Feature | 66 | Phase 4 Deliver | Release 1 (MVP) delivered | An early MVP proves the approach and calibrates estimates for later releases. | Release 1 meets exit criteria and is in use by its intended customers. |  |  | Not started
72 | Story | 71 | Phase 4 Deliver | Release 1: coordinate delivery across teams and partners |  | Dependencies tracked and resolved through the ART Sync. |  |  | Not started
73 | Story | 71 | Phase 4 Deliver | Release 1: complete readiness review |  | Readiness checklist signed off by delivery and operations leads. |  |  | Not started
74 | Story | 71 | Phase 4 Deliver | Release 1: deploy and confirm adoption |  | Release live; adoption measures captured. |  |  | Not started
75 | Story | 71 | Phase 4 Deliver | Release 1: retrospective and estimate recalibration |  | Lessons applied to the roadmap. |  |  | Not started
76 | Feature | 66 | Phase 4 Deliver | Release N delivered (copy per release) | Repeatable releases increase throughput as the team learns. | Release meets exit criteria and is in use by its intended customers. |  |  | Not started
77 | Story | 76 | Phase 4 Deliver | Release N: coordinate delivery across teams and partners |  | Dependencies tracked and resolved through the ART Sync. |  |  | Not started
78 | Story | 76 | Phase 4 Deliver | Release N: complete readiness review |  | Readiness checklist signed off by delivery and operations leads. |  |  | Not started
79 | Story | 76 | Phase 4 Deliver | Release N: deploy and confirm adoption |  | Release live; adoption measures captured. |  |  | Not started
80 | Epic |  | Phase 5 Accept and Go Live | Validation, Acceptance and Go-Live | If every release is tested and accepted by the business before go-live, then trust in the outcome is preserved. |  |  |  | Not started
81 | Feature | 80 | Phase 5 Accept and Go Live | Acceptance and UAT sign-off | Objective acceptance criteria build business confidence. | Each release has test results and business UAT sign-off. |  |  | Not started
82 | Story | 81 | Phase 5 Accept and Go Live | Define acceptance criteria and quality thresholds |  | Criteria agreed with business owners. |  |  | Not started
83 | Story | 81 | Phase 5 Accept and Go Live | Run testing and publish results |  | Results reported against thresholds. |  |  | Not started
84 | Story | 81 | Phase 5 Accept and Go Live | Obtain business UAT sign-off per release |  | Sign-off recorded from each business owner. |  |  | Not started
85 | Feature | 80 | Phase 5 Accept and Go Live | Go-live readiness | A rehearsed go-live with a rollback plan reduces business disruption. | Go-live plan and rollback plan approved; Go/No-Go held and recorded. |  |  | Not started
86 | Story | 85 | Phase 5 Accept and Go Live | Coordinate go-live plan review and approval |  | Plan approved by delivery lead and operations. |  |  | Not started
87 | Story | 85 | Phase 5 Accept and Go Live | Confirm rollback or contingency plan |  | Plan approved and tested where feasible. |  |  | Not started
88 | Story | 85 | Phase 5 Accept and Go Live | Hold Go/No-Go decision meeting |  | Decision recorded in decision log. |  |  | Not started
89 | Epic |  | Cross-cutting | Organizational Change and Communications | If leaders, users and teams hear the right message at the right time, then adoption is faster and resistance is lower. |  |  |  | Not started
90 | Feature | 89 | Cross-cutting | Communication plan executed | Targeted communication reduces surprises and support load. | Communication plan approved and executed on schedule. |  |  | Not started
91 | Story | 90 | Cross-cutting | Complete audience analysis |  | Audiences defined with their needs and preferred channels. |  |  | Not started
92 | Story | 90 | Cross-cutting | Publish leadership update cadence |  | Updates issued on agreed cadence. |  |  | Not started
93 | Story | 90 | Cross-cutting | Publish user communications ahead of each release |  | Notices sent ahead of each go-live. |  |  | Not started
94 | Feature | 89 | Cross-cutting | Training and organizational readiness | Prepared people adopt new ways of working faster. | Skills gaps addressed and role changes communicated before go-live. |  |  | Not started
95 | Story | 94 | Cross-cutting | Complete skills gap assessment |  | Gaps documented per role. |  |  | Not started
96 | Story | 94 | Cross-cutting | Publish training and readiness plan |  | Plan approved with dates and owners. |  |  | Not started
97 | Story | 94 | Cross-cutting | Communicate role and support model changes |  | Changes communicated and acknowledged by affected teams. |  |  | Not started
98 | Epic |  | Phase 6 Close and Sustain | Transition, Closeout and Benefits Realization | If we retire what the program replaces and measure results against the business case, then the organization captures the value it invested for. |  |  |  | Not started
99 | Feature | 98 | Phase 6 Close and Sustain | Transition to operations complete | A clean handoff and retirement of old ways stop duplicate costs. | Operations has accepted ownership; replaced processes, systems and contracts are retired. |  |  | Not started
100 | Story | 99 | Phase 6 Close and Sustain | Hand off support and ownership to operations |  | Operations signs off on the support model. |  |  | Not started
101 | Story | 99 | Phase 6 Close and Sustain | Retire replaced processes, systems or tools |  | Retirement confirmed by owners. |  |  | Not started
102 | Story | 99 | Phase 6 Close and Sustain | Terminate or adjust related contracts |  | Changes confirmed by Procurement. |  |  | Not started
103 | Feature | 98 | Phase 6 Close and Sustain | Benefits realized and program closed | Measuring results proves value and informs future investments. | Benefits report compares actuals to the business case; program closed by steering committee. |  |  | Not started
104 | Story | 103 | Phase 6 Close and Sustain | Measure actual costs and benefits against business case |  | Report reviewed with Finance. |  |  | Not started
105 | Story | 103 | Phase 6 Close and Sustain | Facilitate final Inspect and Adapt and lessons learned |  | Lessons documented and shared. |  |  | Not started
106 | Story | 103 | Phase 6 Close and Sustain | Close program and archive artifacts |  | Steering committee approves closure. |  |  | Not started

## Jira Import
Issue ID | Parent ID | Issue Type | Summary | Description | Labels | Epic Name