## Start Here
Program RAID Log
Risks, Assumptions, Issues, Dependencies and Decisions ¦ SIG Template v1.0
Purpose | One place to track what could go wrong, what we are assuming, what has gone wrong, what we are waiting on, and what has been decided. The program manager reviews it weekly, and the steering committee sees High risks and open escalations.
Preloaded content | Risks, assumptions and dependencies that typically come up in large programs are preloaded as a starting point. They describe common patterns, not predictions. Delete what doesn't apply, and add client-specific items in the empty rows.
Scoring | Probability and Impact are left blank on purpose. The program team scores each risk from 1 to 5 using the Scoring Guide tab. Score and Rating calculate automatically.
Columns to fill in | Yellow cells. ID, Score and Rating calculate automatically.
Cadence | Weekly RAID review with Program Leadership; High risks go to the steering committee (see the Governance Charter, Sections 6 and 10).
Pairs with | SIG Governance Charter and RACI, SIG Program Jira Accelerator (link items in the 'Linked Jira item' column), and the SIG Business Case and TCO Template.
© 2026 Stephens Insight Group LLC. Capital In. Value Out. ¦ stephensinsightgroup.com

## Risks
ID | Category | Risk (If ... then ...) | Phase | Probability (1-5) | Impact (1-5) | Score | Rating | Owner | Mitigation | Contingency / trigger | Status | Date raised | Last reviewed | Linked Jira item
R-001 | Schedule | If a hard date (contract renewal, regulatory or fiscal deadline) arrives before the program delivers, then the organization faces penalties, extension costs or compliance exposure. | Mobilize |  |  |  | Not scored |  | Confirm constraint dates in week 1; plan releases backward from them; negotiate fallback options early. | Trigger: any milestone slip that pushes delivery past the constraint date. | Open
R-002 | Scope | If impacted teams, customers or processes are not fully identified, then the program will miss requirements and disrupt people at go-live. | Discover |  |  |  | Not scored |  | Run SIPOC and stakeholder mapping; require a named owner for every impacted group. | Add an impact review to each release readiness check. | Open
R-003 | Technical | If the work is more complex than estimated, then effort and timeline will overrun. | Discover |  |  |  | Not scored |  | Baseline the current state before estimating; use the first release to recalibrate. | Re-sequence releases; add capacity. | Open
R-004 | People | If key subject matter experts leave or are pulled to other work, then critical knowledge is lost. | All |  |  |  | Not scored |  | Identify key-person dependencies; document knowledge early; agree availability with leadership. | Engage backup experts or contractors. | Open
R-005 | People | If business owners are not available for requirements and UAT, then sign-off and go-live are delayed. | Accept |  |  |  | Not scored |  | Book UAT time at PI Planning; name owners in the RACI; escalate availability through the steering committee. | Trigger: UAT not started within agreed window. | Open
R-006 | Financial | If future-state run costs exceed estimates, then the business case erodes. | Decide |  |  |  | Not scored |  | Set cost guardrails and monthly cost reviews before the first release. | Trigger: spend above guardrail; optimize or rescope. | Open
R-007 | Financial | If the transition period lasts longer than planned, then the organization pays for old and new ways of working longer than the business case assumes. | Deliver |  |  |  | Not scored |  | Track current-state cost by release in the business case; make retirement an exit criterion. | Escalate slips beyond tolerance. | Open
R-008 | Quality | If releases go live with significant defects, then user trust and adoption drop. | Accept |  |  |  | Not scored |  | Agree acceptance criteria and quality thresholds up front; publish test results before each Go/No-Go. | Hold go-live until thresholds are met. | Open
R-009 | Technical | If the solution does not meet performance or usability expectations, then users reject it. | Deliver |  |  |  | Not scored |  | Identify critical needs early; test them in the first release. | Tune or adjust before go-live; keep rollback plan. | Open
R-010 | Compliance | If security, privacy or legal approvals take longer than planned, then releases are blocked. | Decide |  |  |  | Not scored |  | Engage Security and Legal in discovery; schedule high-risk scope in later releases. | Escalate through steering committee. | Open
R-011 | Vendor | If vendors or partners lack capacity or the right skills, then delivery slows. | Mobilize |  |  |  | Not scored |  | Confirm named resources and skills in the SOW; review partner performance each PI. | Invoke SOW remedies; add alternate partner. | Open
R-012 | Scope | If teams add new requests mid-program, then scope grows and dates slip. | Deliver |  |  |  | Not scored |  | Apply change control and tolerances in the charter; keep a separate backlog for later enhancements. | Steering committee decision on any addition. | Open
R-013 | Resourcing | If competing priorities pull team members away, then velocity drops. | All |  |  |  | Not scored |  | Secure dedicated capacity at PI Planning; make conflicts visible in the ART Sync. | Escalate to sponsor. | Open
R-014 | Governance | If major decisions are reopened after planning, then rework and delay follow. | Decide |  |  |  | Not scored |  | Record decisions and rationale in the decision log; communicate them broadly. | Steering committee only may reopen. | Open
R-015 | Readiness | If environments, tools or access are not ready before the first release, then teams are blocked. | Ready |  |  |  | Not scored |  | Treat readiness as an enabler Epic with its own milestones; track weekly. | Re-sequence work while readiness completes. | Open
R-016 | Change | If people are comfortable with current ways of working, then adoption lags. | All |  |  |  | Not scored |  | Execute the communication plan; involve champions; show quick wins at System Demos. | Targeted coaching for lagging groups. | Open
R-017 | Compliance | If retention, contract or policy obligations for the current state are not identified, then it cannot be fully retired. | Discover |  |  |  | Not scored |  | Confirm obligations with Legal, Records and Procurement during discovery. | Plan a limited retention arrangement pending decision. | Open
R-018 | Scope | If upstream systems, processes or policies change during the program, then the target keeps moving. | Deliver |  |  |  | Not scored |  | Agree a change notification process with upstream owners. | Add impact checks to each release. | Open
R-019 | Governance | If decision rights are unclear, then decisions stall. | Mobilize |  |  |  | Not scored |  | Approve the governance charter and RACI before PI 1. | Escalation path in the charter. | Open
R-020 | People | If the teams who will run the solution lack the skills to support it, then results fade after the program closes. | All |  |  |  | Not scored |  | Skills gap assessment and training plan; pair internal staff with vendors. | Extend vendor support for transition. | Open
R-021 | [6 empty] | Not scored
R-022 | [6 empty] | Not scored
R-023 | [6 empty] | Not scored
R-024 | [6 empty] | Not scored
R-025 | [6 empty] | Not scored
R-026 | [6 empty] | Not scored
R-027 | [6 empty] | Not scored
R-028 | [6 empty] | Not scored
R-029 | [6 empty] | Not scored
R-030 | [6 empty] | Not scored
R-031 | [6 empty] | Not scored
R-032 | [6 empty] | Not scored
R-033 | [6 empty] | Not scored
R-034 | [6 empty] | Not scored
R-035 | [6 empty] | Not scored

## Assumptions
ID | Assumption | Impact if wrong | Owner | Validate by | Status | Notes
A-001 | The executive sponsor remains in role through program closeout. | Decisions slow; program loses priority. |  |  | Open
A-002 | Funding is approved for the full program, not only the first PI. | Releases stall midway, extending transition costs. |  |  | Open
A-003 | The selected solution direction will not be reopened. | Rework of designs and plans. |  |  | Open
A-004 | The current state remains supported and stable until it is replaced. | Unplanned remediation or extension costs. |  |  | Open
A-005 | Business owners will provide time for discovery and UAT. | Sign-off and go-live delays. |  |  | Open
A-006 | Vendors and partners are contracted and staffed by [date]. | Mobilization slips. |  |  | Open
A-007 | Upstream systems, processes and policies remain stable or changes follow an agreed notification process. | Rework of completed Features. |  |  | Open
A-008 | The program will use the organization's existing PI and iteration cadence. | Misaligned planning with other teams. |  |  | Open
A-009
A-010
A-011
A-012
A-013
A-014
A-015
A-016
A-017
A-018
A-019
A-020
A-021
A-022
A-023

## Issues
ID | Issue | Impact | Priority | Owner | Action plan | Escalation level | Date raised | Target resolution | Status | Linked risk / Jira
I-001 | EXAMPLE (delete): Access to [system] has not been granted, so the current state baseline cannot be completed. | Discovery delayed; release roadmap at risk. | High |  | Request access through the system owner; escalate to Program Leadership if not granted within [x] days. | 2 - Program Leadership |  |  | Open | R-002
I-002
I-003
I-004
I-005
I-006
I-007
I-008
I-009
I-010
I-011
I-012
I-013
I-014
I-015
I-016

## Dependencies
ID | Dependency | Type | Needed by (team) | Provided by (team) | Needed by date | Owner | Status | Linked Jira item | Notes
D-001 | Environments, tools and access ready before the first release | Internal | Delivery teams | IT / Infrastructure |  |  | Open
D-002 | Security approval of access model before using sensitive information | Internal | Delivery teams | Security and Compliance |  |  | Open
D-003 | Vendor or partner contracts signed and resources onboarded | External | Program | Procurement / Vendor |  |  | Open
D-004 | Contract renewal and notice terms confirmed for anything being replaced | External | Program | Procurement |  |  | Open
D-005 | Capacity from shared teams to support each release | Internal | Delivery teams | Shared service teams |  |  | Open
D-006 | Upstream owners confirm interfaces and inputs | Internal | Delivery teams | Upstream owners |  |  | Open
D-007 | Policy or compliance decisions made before affected releases | Internal | Release planning | Compliance / Legal |  |  | Open
D-008 | Finance approval of budget before PI 1 | Internal | Program | Finance |  |  | Open
D-009 | Training delivered before each go-live | Internal | Users | Program / Change Management |  |  | Open
D-010 | Retention and contract decisions made before retiring the current state | Internal | Closeout | Records / Legal |  |  | Open
D-011
D-012
D-013
D-014
D-015
D-016
D-017
D-018
D-019
D-020
D-021
D-022
D-023
D-024
D-025

## Decision Log
ID | Decision | Options considered | Rationale | Decided by | Forum | Date | Impacted items
X-001 | EXAMPLE (delete): Release 1 (MVP) will include [scope]. | [Option A], [Option B] | Highest WSJF score with the lowest delivery risk. | Product Manager | PI Planning
X-002
X-003
X-004
X-005
X-006
X-007
X-008
X-009
X-010
X-011
X-012
X-013
X-014
X-015
X-016

## Scoring Guide
Risk Scoring Guide
Score = Probability x Impact. Rating: High 15 to 25, Medium 8 to 14, Low 1 to 7. Adjust the definitions to the client's risk framework if they have one.
Score | Probability | Impact | Heat map (Probability down, Impact across)
1 | Rare: very unlikely during the program | Minimal: absorbed within the team |  | 1 | 2 | 3 | 4 | 5
2 | Unlikely | Minor: small delay or cost within tolerance | 5 | 5 | 10 | 15 | 20 | 25
3 | Possible | Moderate: affects a milestone or release; needs Program Leadership | 4 | 4 | 8 | 12 | 16 | 20
4 | Likely | Major: exceeds a tolerance; steering committee decision needed | 3 | 3 | 6 | 9 | 12 | 15
5 | Almost certain or already emerging | Severe: threatens the business case, compliance or a hard deadline | 2 | 2 | 4 | 6 | 8 | 10
|  |  | 1 | 1 | 2 | 3 | 4 | 5