## Start Here
Program RAID Log
Risks, Assumptions, Issues, Dependencies and Decisions ¦ SIG Template v1.3
Quick start | 1. Review the 10 starter risks, 8 assumptions and 10 dependencies; delete what does not apply and add your own. 2. Score each risk 1 to 5 for Probability and Impact using the scoring guide to the right of the Risks table. 3. Review the log weekly with Program Leadership and take High risks to the steering committee.
Example | Issue: access to [system] has not been granted, so discovery is delayed. Decision: Release 1 (MVP) will include [scope], chosen for the highest WSJF score.
© 2026 Stephens Insight Group LLC. Capital In. Value Out. ¦ stephensinsightgroup.com

## Risks
ID | Category | Risk (If ... then ...) | Phase | Probability (1-5) | Impact (1-5) | Score | Rating | Owner | Mitigation | Contingency / trigger | Status | Date raised | Last reviewed | Linked Jira item | Score | Probability | Impact
| Schedule | If a hard date (contract renewal, regulatory or fiscal deadline) arrives before the program delivers, then the organization faces penalties, extension costs or compliance exposure. | Mobilize | [5 empty] | Confirm constraint dates in week 1; plan releases backward from them; negotiate fallback options early. | Trigger: any milestone slip that pushes delivery past the constraint date. | Open |  |  |  | 1 | Rare: very unlikely during the program | Minimal: absorbed within the team
| Scope | If impacted teams, customers or processes are not fully identified, then the program will miss requirements and disrupt people at go-live. | Discover | [5 empty] | Run SIPOC and stakeholder mapping; require a named owner for every impacted group. | Add an impact review to each release readiness check. | Open |  |  |  | 2 | Unlikely | Minor: small delay or cost within tolerance
| Technical | If the work is more complex than estimated, then effort and timeline will overrun. | Discover | [5 empty] | Baseline the current state before estimating; use the first release to recalibrate. | Re-sequence releases; add capacity. | Open |  |  |  | 3 | Possible | Moderate: affects a milestone or release; needs Program Leadership
| People | If business owners are not available for requirements and UAT, then sign-off and go-live are delayed. | Accept | [5 empty] | Book UAT time at PI Planning; name owners in the RACI; escalate availability through the steering committee. | Trigger: UAT not started within agreed window. | Open |  |  |  | 4 | Likely | Major: exceeds a tolerance; steering committee decision needed
| Compliance | If security, privacy or legal approvals take longer than planned, then releases are blocked. | Decide | [5 empty] | Engage Security and Legal in discovery; schedule high-risk scope in later releases. | Escalate through steering committee. | Open |  |  |  | 5 | Almost certain or already emerging | Severe: threatens the business case, compliance or a hard deadline
| Vendor | If vendors or partners lack capacity or the right skills, then delivery slows. | Mobilize | [5 empty] | Confirm named resources and skills in the SOW; review partner performance each PI. | Invoke SOW remedies; add alternate partner. | Open
| Scope | If teams add new requests mid-program, then scope grows and dates slip. | Deliver | [5 empty] | Apply change control and tolerances in the charter; keep a separate backlog for later enhancements. | Steering committee decision on any addition. | Open |  |  |  | Score = Probability x Impact. Rating: High 15 to 25, Medium 8 to 14, Low 1 to 7.
| Resourcing | If competing priorities pull team members away, then velocity drops. | All | [5 empty] | Secure dedicated capacity at PI Planning; make conflicts visible in the ART Sync. | Escalate to sponsor. | Open |  |  |  | Adjust the definitions to your organization’s risk framework if it has one.
| Readiness | If environments, tools or access are not ready before the first release, then teams are blocked. | Ready | [5 empty] | Treat readiness as an enabler Epic with its own milestones; track weekly. | Re-sequence work while readiness completes. | Open
| Change | If people are comfortable with current ways of working, then adoption lags. | All | [5 empty] | Execute the communication plan; involve champions; show quick wins at System Demos. | Targeted coaching for lagging groups. | Open

## Assumptions
ID | Assumption | Impact if wrong | Owner | Validate by | Status | Notes
| The executive sponsor remains in role through program closeout. | Decisions slow; program loses priority. |  |  | Open
| Funding is approved for the full program, not only the first PI. | Releases stall midway, extending transition costs. |  |  | Open
| The selected solution direction will not be reopened. | Rework of designs and plans. |  |  | Open
| The current state remains supported and stable until it is replaced. | Unplanned remediation or extension costs. |  |  | Open
| Business owners will provide time for discovery and UAT. | Sign-off and go-live delays. |  |  | Open
| Vendors and partners are contracted and staffed by [date]. | Mobilization slips. |  |  | Open
| Upstream systems, processes and policies remain stable or changes follow an agreed notification process. | Rework of completed Features. |  |  | Open
| The program will use the organization's existing PI and iteration cadence. | Misaligned planning with other teams. |  |  | Open

## Issues
ID | Issue | Impact | Priority | Owner | Action plan | Escalation level | Date raised | Target resolution | Status | Linked risk / Jira

## Dependencies
ID | Dependency | Type | Needed by (team) | Provided by (team) | Needed by date | Owner | Status | Linked Jira item | Notes
| Environments, tools and access ready before the first release | Internal | Delivery teams | IT / Infrastructure |  |  | Not started
| Security approval of access model before using sensitive information | Internal | Delivery teams | Security and Compliance |  |  | Not started
| Vendor or partner contracts signed and resources onboarded | External | Program | Procurement / Vendor |  |  | Not started
| Contract renewal and notice terms confirmed for anything being replaced | External | Program | Procurement |  |  | Not started
| Capacity from shared teams to support each release | Internal | Delivery teams | Shared service teams |  |  | Not started
| Upstream owners confirm interfaces and inputs | Internal | Delivery teams | Upstream owners |  |  | Not started
| Policy or compliance decisions made before affected releases | Internal | Release planning | Compliance / Legal |  |  | Not started
| Finance approval of budget before PI 1 | Internal | Program | Finance |  |  | Not started
| Training delivered before each go-live | Internal | Users | Program / Change Management |  |  | Not started
| Retention and contract decisions made before retiring the current state | Internal | Closeout | Records / Legal |  |  | Not started

## Decision Log
ID | Decision | Options considered | Rationale | Decided by | Forum | Date | Impacted items