## Workshop Checklist
Strategic Themes Workshop Checklist
Jira import view. Assignees are role placeholders; replace with Jira user emails before importing. Story points are suggested sizes.
# | Phase | Issue Type | Summary | Description | Acceptance Criteria | Story Points | Assignee | Labels | Issue Id | Parent
| Workshop | Epic | Strategic Themes Workshop Checklist | Workshop Checklist for planning, running, and following up on a Strategic Themes workshop. Purpose: Identify and articulate 3 to 5 Strategic Themes that reflect the organization's most important business objectives for the planning horizon ahead. Timing: Run at the start of each planning horizon, ideally 4 to 6 weeks before PI Planning. Allow 3 to 4 hours for the session. Core participants: Executive Leadership, Portfolio Manager, Business Owners, Epic Owners (6 to 10 people). |  |  | Facilitator | strategic-themes, workshop-checklist, workshop, role-facilitator | ST-00
1 | Preparation | Task | Gather and review enterprise strategic inputs | Collect and review the current enterprise strategic plan, annual objectives, and any available market or competitive analysis. Themes must be grounded in real strategic intent, not generated in a vacuum. | • Current strategic plan and annual objectives are collected • Available market and competitive analysis is collected • Existing OKRs or business objectives are identified • Facilitator has reviewed all inputs and noted key priorities | 3 | Facilitator | strategic-themes, workshop-checklist, phase-preparation, role-facilitator | ST-01 | ST-00
2 | Preparation | Task | Confirm executive participation | Secure commitment from senior leadership before scheduling the session. Strategic Themes created without senior leadership input are unlikely to survive the budget and prioritization process. | • Executive sponsor(s) have committed to attend • Key Executive Leadership attendees are confirmed before the invite goes out | 2 | Facilitator | strategic-themes, workshop-checklist, phase-preparation, role-facilitator | ST-02 | ST-00
3 | Preparation | Task | Prepare the Facilitator Presentation and Excel Template | Download and prepare the Strategic Themes Facilitator Presentation and the Strategic Themes Excel Template from the SIG workshop guide. Tailor them with the organization's strategic context. | • Facilitator Presentation is downloaded and customized for this organization • Strategic Themes Excel Template is downloaded and ready to capture themes, OKRs, and portfolio implications | 3 | Facilitator | strategic-themes, workshop-checklist, phase-preparation, role-facilitator | ST-03 | ST-00
4 | Preparation | Task | Schedule the workshop | Schedule the session: time, attendees, location, and access to collaboration tools. Book 3 to 4 hours, ideally 4 to 6 weeks before PI Planning. Use the email and calendar invite templates on the workshop guide. | • Calendar invite is sent to all 6 to 10 core participants • Session is 3 to 4 hours and falls 4 to 6 weeks before PI Planning • Location or virtual meeting link and collaboration tool access are included | 1 | Facilitator | strategic-themes, workshop-checklist, phase-preparation, role-facilitator | ST-04 | ST-00
5 | Preparation | Task | Send the pre-read package | Send a pre-read package that includes strategic context, market data, and any existing OKRs or business objectives. | • Pre-read package is sent to all participants • Package includes strategic context, market and competitive data, and current OKRs or business objectives | 2 | Facilitator | strategic-themes, workshop-checklist, phase-preparation, role-facilitator | ST-05 | ST-00
6 | Preparation | Task | Ask participants to prepare their top strategic priorities | Ask each participant to come prepared with their perspective on the 2 to 3 most critical strategic priorities for the next planning horizon. | • Request is sent to every participant • Participants know they will share 2 to 3 priorities during the session | 1 | Facilitator | strategic-themes, workshop-checklist, phase-preparation, role-facilitator | ST-06 | ST-00
7 | Preparation | Task | Confirm attendance | Confirm attendance 1 to 2 days before the session and resolve any scheduling conflicts with executive participants. | • Attendance is confirmed 1 to 2 days prior • Any executive scheduling conflicts are resolved or the session is rescheduled | 1 | Facilitator | strategic-themes, workshop-checklist, phase-preparation, role-facilitator | ST-07 | ST-00
8 | Preparation | Task | Set up the room and technology | Physical: large whiteboard or printed canvas, U-shape or boardroom seating, sticky notes for brainstorming. Virtual: Miro or Mural with a pre-built Strategic Themes canvas, board access for all participants, breakout rooms for small-group drafting. Have the strategic plan, market data, and existing OKRs visible and accessible during the session. | • Room or virtual canvas is ready before participants arrive • All participants have confirmed board access (virtual) • Breakout rooms are enabled (virtual) • All technology has been tested • Strategic input materials are visible during the session | 2 | Facilitator | strategic-themes, workshop-checklist, phase-preparation, role-facilitator | ST-08 | ST-00
9 | Facilitation | Task | Agenda 1: Strategic Context Review | Open the session with its purpose and expected outcome. Review the enterprise strategic plan, market conditions, and competitive landscape. Surface any recent changes to organizational direction or business priorities. | • Strategic plan, market conditions, and competitive landscape are reviewed with the group • Recent changes to direction or priorities are captured | 2 | Facilitator | strategic-themes, workshop-checklist, phase-facilitation, role-facilitator | ST-09 | ST-00
10 | Facilitation | Task | Agenda 2: Individual Priority Input | Each participant shares their view on the top 2 to 3 strategic priorities for the planning horizon. Capture inputs without debate; discussion comes later. | • Every participant has shared 2 to 3 priorities • All inputs are captured on the canvas without debate | 1 | Facilitator | strategic-themes, workshop-checklist, phase-facilitation, role-facilitator | ST-10 | ST-00
11 | Facilitation | Task | Agenda 3: Theme Identification and Grouping | Identify common threads and group related priorities into candidate themes. Draft initial theme statements broad enough to guide multiple initiatives. If a theme sounds like a project title, it is probably too narrow. | • Related priorities are grouped into candidate themes • Each candidate theme has a draft statement • No candidate theme describes a single project | 2 | Facilitator | strategic-themes, workshop-checklist, phase-facilitation, role-facilitator | ST-11 | ST-00
12 | Facilitation | Task | Agenda 4: Theme Refinement and Alignment | Refine theme statements for clarity, strategic relevance, and measurability. Resolve disagreements about priority and scope through open dialogue. Aim for 3 to 5 themes; more than 5 to 6 loses the prioritization signal. | • 3 to 5 themes are agreed by leadership • Each theme statement is clear, strategically relevant, and measurable • Disagreements on priority and scope are resolved or documented | 3 | Facilitator | strategic-themes, workshop-checklist, phase-facilitation, role-facilitator | ST-12 | ST-00
13 | Facilitation | Task | Agenda 5: OKR and Measurement Definition | Define 1 to 3 key results for each theme that will signal strategic progress. Confirm measurement frequency and ownership. | • Every theme has 1 to 3 key results • Measurement frequency is agreed for each key result • An owner is named for each key result | 3 | Facilitator | strategic-themes, workshop-checklist, phase-facilitation, role-facilitator | ST-13 | ST-00
14 | Facilitation | Task | Agenda 6: Portfolio Implications Review | Discuss how each theme should influence portfolio backlog prioritization and ART investment. Confirm the communication plan for sharing themes with ARTs and teams. | • Portfolio and ART investment implications are documented for each theme • Communication plan for ARTs and teams is confirmed with owners and dates • Themes, rationale, OKRs, and implications are recorded in the Excel Template | 2 | Portfolio Manager | strategic-themes, workshop-checklist, phase-facilitation, role-portfolio-manager | ST-14 | ST-00
15 | Follow-Up | Task | Send the follow-up communication | Send the post-workshop communication to participants and stakeholders using the Follow-Up Communication Template on the workshop guide. | • Follow-up communication is sent to all participants • Includes the finalized themes, OKRs, and agreed next steps | 1 | Facilitator | strategic-themes, workshop-checklist, phase-follow-up, role-facilitator | ST-15 | ST-00
16 | Follow-Up | Task | Hold a validation session (if needed) | Optional. If themes need broader organizational input before being finalized, run a shorter validation session with Business Owners and Epic Owners. | • Decision on whether validation is needed is recorded • If held, feedback is captured and themes are finalized | 3 | Facilitator | strategic-themes, workshop-checklist, phase-follow-up, role-facilitator | ST-16 | ST-00
17 | Follow-Up | Task | Communicate finalized themes to all ARTs and teams | Communicate the finalized Strategic Themes to all ARTs, Scrum Teams, and portfolio stakeholders before PI Planning. Themes should be visible, understood, and actively referenced. | • Themes are shared with every ART, team, and portfolio stakeholder • Communication happens before PI Planning • Themes are posted in a visible, shared location | 2 | Portfolio Manager | strategic-themes, workshop-checklist, phase-follow-up, role-portfolio-manager | ST-17 | ST-00
18 | Follow-Up | Task | Integrate themes into PI Planning | Use the themes as the lens for evaluating Program Objectives and backlog priorities during PI Planning. | • PI Planning materials reference the Strategic Themes • Program Objectives and backlog priorities are evaluated against the themes | 3 | Business Owner | strategic-themes, workshop-checklist, phase-follow-up, role-business-owner | ST-18 | ST-00
19 | Follow-Up | Task | Review portfolio epics against the themes | Review portfolio epics and initiatives against the themes. Deprioritize or eliminate work that does not advance any Strategic Theme. | • Every active portfolio epic is mapped to a theme or flagged • Work that advances no theme is deprioritized or removed, with decisions recorded | 5 | Portfolio Manager | strategic-themes, workshop-checklist, phase-follow-up, role-portfolio-manager | ST-19 | ST-00
20 | Follow-Up | Task | Track OKR progress quarterly | Track OKR progress at least quarterly and communicate results to leadership and portfolio stakeholders. | • A quarterly OKR review cadence is scheduled • Results are shared with leadership and portfolio stakeholders each quarter | 3 | Portfolio Manager | strategic-themes, workshop-checklist, phase-follow-up, role-portfolio-manager | ST-20 | ST-00
21 | Follow-Up | Task | Review and refresh themes each planning horizon | Review and refresh themes at the start of each planning horizon, at least annually, or when significant strategic shifts occur. | • Next theme review is scheduled • Triggers for an off-cycle refresh (market or strategy shift) are agreed | 2 | Executive Leadership | strategic-themes, workshop-checklist, phase-follow-up, role-executive-leadership | ST-21 | ST-00
22 | Follow-Up | Task | Use themes in Lean Portfolio Management events | Use the themes in Lean Portfolio Management (LPM) events to guide investment allocation across value streams and ARTs. | • Themes are a standing input to LPM events • Investment allocation decisions reference the themes | 3 | Portfolio Manager | strategic-themes, workshop-checklist, phase-follow-up, role-portfolio-manager | ST-22 | ST-00
23 | Follow-Up | Task | Celebrate and communicate progress against themes | Celebrate and communicate progress against themes to reinforce the connection between daily delivery and enterprise strategy. | • Progress updates tied to themes are shared with teams on a regular cadence • Wins that advance a theme are recognized | 2 | Executive Leadership | strategic-themes, workshop-checklist, phase-follow-up, role-executive-leadership | ST-23 | ST-00
[5 empty] | Total story points | 52
Source: SIG Strategic Themes Workshop Guide, https://stephensinsightgroup.com/resources-tools/workshops/strategic-themes-workshop/